## CSG
Runbook
ID | Track | Task | Start | End | Status | Comments from Protiviti | Task Owner | Comments from Sandhya/Param
1 | Governance | Onboarding /Access for new joiners- Documents to be shared | 2026-07-20 | 2026-07-21 | In-progress
2 | Requirements | UI/UX wireframes — Portal, Dashboard, Trade Detail, Compare & Match | 2026-07-01 | 7th july | Review awaited |  | Satya
3 | Requirements | Onboarding Wizard functional spec | 2026-07-01 | 2026-07-08 | In Progress |  | Aastha
4 | Requirements | Architecture diagram -logical | 2026-07-07 | 2026-07-13 | In Progress | Rakesh to check about few components with Santosh on ServiceNow | Rakesh
5 | Build | Graph API - | - | -
6 | Admin | Access to eval instance- yet to be granted with capabilities | 2026-07-02 | - | In Progress
7 | Governance | API access- PCM read only | 2026-07-15 | 2026-07-18 | In Progress
8 | Requirements | Define Workflow end-to-end | 2026-07-17 | 2026-07-21 | In Progress |  | Aastha/Satya
9 | Both BA + Dev team | Obtain inbox shared access including the sample mails with Excel, muti-threads | 2026-07-17 | 2026-07-20 | In Progress
10 | Requirements | Define capability Contracts(typed input/output,configuration schema,idempotency ) for all capabilities | 2026-07-17 | 2026-07-22 | YTS |  | Satya/Rakesh
11 | Requirements | Test data annotation | 2026-07-03 | 2026-07-17 | Done | captured upto (17th July/2026) | Aastha
12 | Requirements | Golden source/set creation | 2026-07-07 | - | In Progress |  | Aastha | Not a blocker
13 | Requirements | Full synthetic + masked production-like dataset | 2026-07-07 | 2026-07-13 | Done |  | Akshit | Data consisted actual client/counterparty names and was not masked. Hence, discontinued
14 | Requirements | Collaboration with OpsTeam (for user scenarios) | 2026-07-21 |  | YTS |  | Aastha/Satya
15 | Build | Transformation Engine- background research ,iterate & show to IT team | 2026-07-17 | 2026-07-23 | In Progress |  | Manav
16 | Build | Capability 1 - Email ingestion | 2026-07-17 | 2026-07-24 | YTS | On-hold by Bhusan | Manav
17 | Build | Test Snow flows | 2026-07-17 | 2026-07-20 | YTS |  | Akshit
18 | Build | Test Snow Actions | 2026-07-20 | 2026-07-22 | YTS |  | Akshit
19 | Build | Verify that an SNOW action can be called within a Snow flow | 2026-07-21 | 2026-07-23 | YTS |  | Akshit
20 | Build | Verify that a flow(subflow) can be called within another flow | 2026-07-22 | 2026-07-24 | YTS |  | Akshit
21 | Build | Create a hosted FastAPI endpoint and invoke it from SNOW | 2026-07-24 | 2026-07-27 | YTS |  | Akshit
22 | Build | Create a SNOW workflow and an action with a GenAI/LLM call | 2026-07-26 | 2026-07-27 | YTS |  | Akshit
23 | Build | Validate all features through the SNOW UI | 2026-07-28 | 2026-07-30 | YTS |  | Akshit
24 | Build | Idependent platform - code to standardised datatype | 2026-07-20 | 2026-07-22 | In-progress |  | Manav
25 |  | Mock Data | 2026-07-20 | 2026-07-21 | Completed |  | Akshit