## Claude
Master Component & Feature Inventory — POC state, production target, gaps, priority
ID | Layer / Module | Component / Feature | Description (what it does) | Current POC Implementation | Production-Ready Target / Enhancements | Key Gaps to Address | Priority | Effort | Type
C01 | Frontend (SPA) | Login / Signup screen | Username/password auth UI with JWT, reviewer self-signup, animated brand hero. | Vanilla-JS screen; token in sessionStorage; animated bars/sparkline/pie. | SSO/OIDC login option, password rules, error states, 'forgot password', branded but framework-based. | No password reset, no MFA, client validation only. | P1 - High | M | Enhance
C02 | Frontend (SPA) | App shell / role-based navigation | Sidebar + topbar, role-aware menu (admin vs reviewer), user dropdown/logout. | Hand-built nav in app.js; nav items toggled by role. | Same UX on a maintainable component framework + design system. | Monolithic 3,600-line app.js; hard to maintain/test. | P2 - Medium | M | Enhance
C03 | Frontend (SPA) | Welcome / rule-engine overview | Landing page summarizing rule engine (scenarios, categories, status) with chart + table. | Renders /api/rules; Plotly bar chart; category filter. | Keep; move charts to shared chart service. | Static content tied to in-memory data. | P3 - Future | S | Existing
C04 | Frontend (SPA) | Executive Summary dashboard | KPIs + category breach bars, donut, risk heatmap, top-10, treemap. | Plotly charts from /api/data/summary; DOM page cache. | Server-side aggregation, cached, export-to-image. | Heavy client compute; recomputed each load. | P2 - Medium | M | Enhance
C05 | Frontend (SPA) | Category Deep Dive | Per-category KPIs and scenario breach-rate comparison. | Client filter of master data + Plotly. | Keep; back with query API. | Depends on full dataset in memory. | P3 - Future | S | Existing
C06 | Frontend (SPA) | Scenario Drill-Down | Record-level table per scenario: server pagination, sort, search, breach filter, breach-reason chart, rule info. | /api/data/scenario with pagination params; Plotly donut + reasons. | Keep; add column-level export, saved views. | Search scans all columns each call (no index). | P2 - Medium | M | Enhance
C07 | Frontend (SPA) | Rules Library (thresholds) | View all rules; edit threshold values; apply/reset to recalc breaches live. | Editable table → /api/data/params; recompute in memory. | Versioned thresholds, approval workflow, audit of changes, persisted per environment. | Threshold changes not persisted or audited. | P1 - High | M | Enhance
C08 | Frontend (SPA) | Custom Rules Builder (LLM) | Admin builds breach rules in plain English; LLM writes SQL WHERE; preview matches; CRUD. | NL→SQL via /api/custom-rules; preview against uploaded data. | Rule governance, test harness, approval, change history, rollback. | No approval/versioning; relies on blocklist validation. | P1 - High | L | Enhance
C09 | Frontend (SPA) | Exception Report | Multiselect filters (category/scenario/status); export CSV & Excel. | /api/reports/exception (+csv/excel) with multiselects. | Keep; large-export streaming + async generation. | Builds full DataFrame in memory. | P2 - Medium | S | Existing
C10 | Frontend (SPA) | Trend Analysis | Time-series breach trends, regression trend line, category heatmap over time, top movers, stacked bars. | /api/data/trend; date auto-detection; Plotly. | Keep; precompute periods server-side. | Date detection heuristic; client aggregation. | P3 - Future | M | Existing
C11 | Frontend (SPA) | Causality Analysis | Co-occurrence matrix, Jaccard pairs, repeat offenders, influence scores, category chains across shared IDs. | /api/data/causality; matrix + tables + heatmaps. | Keep; offload heavy set math to backend jobs. | O(n²) compute on request; memory bound. | P3 - Future | M | Existing
C12 | Frontend (SPA) | Comparison Mode | Upload a second file (e.g. prior month) and diff scenarios/categories. | 2nd file to in-memory store; /api/data/comparison diff. | Persist datasets/periods; compare any two stored runs. | Comparison file also held in memory only. | P2 - Medium | M | Enhance
C13 | Frontend (SPA) | Assignment Manager (admin) | Assign breach records to reviewers; list/filter; status; user management; duplicate detection. | /api/assignments + comments/documents + /api/users. | Keep; add notifications, SLA timers, bulk assign. | No notifications; per-record indices fragile across re-uploads. | P1 - High | M | Enhance
C14 | Frontend (SPA) | Reviewer Dashboard | Reviewer sees assignments, updates status, uploads evidence docs, comments. | /api/assignments filtered by user; doc upload; comments. | Keep; notifications, audit, e-sign of resolution. | No notifications/audit trail. | P1 - High | M | Enhance
C15 | Frontend (SPA) | SQL GPT page (embedded) | Chat UI: upload data, ask NL questions, see generated SQL + results, export. | Re-implemented in app.js; calls /sql-gpt-api. | Unify with standalone; auth-gate; governed LLM. | Duplicated UI; endpoints unauthenticated. | P1 - High | M | Enhance
C16 | Frontend (SPA) | Shared UI widgets | Sortable tables, tabs, multiselect, accordion, toasts, KPI cards, Plotly wrapper, downloads. | Hand-rolled helpers in app.js. | Component library / design system, unit-tested. | No tests; CDN-loaded Plotly (no offline/version pin). | P2 - Medium | M | Enhance
C17 | Frontend (SPA) | Frontend build & delivery | Serving of HTML/CSS/JS assets. | Static files served by FastAPI; cache-busting via ?v=. | Bundler (Vite), minify, hash, CDN, SRI, versioning. | No build pipeline; manual cache-busting. | P2 - Medium | M | New
C18 | Backend API (AIM) | Authentication endpoints | Login, signup, current-user; JWT issue/verify (HS256). | jose JWT; default secret w/ warning; 24h expiry. | Strong secret from vault, refresh tokens, lockout, MFA/SSO. | Insecure default secret; no refresh/lockout. | P0 - Critical | M | Enhance
C19 | Backend API (AIM) | Authorization / RBAC | Admin vs reviewer gating (require_admin) on sensitive routes. | Role claim in JWT; dependency guards. | Central RBAC matrix, least-privilege, per-resource checks. | Coarse roles; some routes lack ownership checks. | P1 - High | M | Enhance
C20 | Backend API (AIM) | Data upload & ingest | Accept AIM Excel, parse all sheets, apply rules, build summary. | /api/data/upload → in-memory per-user store. | Async ingest job, validation, virus scan, persisted datasets. | Synchronous; whole dataset in RAM; no validation/scan. | P0 - Critical | L | Enhance
C21 | Backend API (AIM) | In-memory data store | Holds each user's DataFrames, params, comparison data. | Python dict keyed by user id (_user_data). | Replace with DB + cache; stateless API workers. | Lost on restart; breaks multi-worker/scale; memory blow-up. | P0 - Critical | L | Enhance
C22 | Backend API (AIM) | Summary / scenario / params APIs | Serve summary, paginated scenario data, threshold params. | Compute from in-memory store on each call. | Query persisted store; cache; pagination everywhere. | Recompute per request; coupled to memory store. | P1 - High | M | Enhance
C23 | Backend API (AIM) | Threshold update / reset | Recompute breaches when thresholds change/reset. | reapply_rules over in-memory data. | Persist threshold sets, audit, async recompute for big data. | Not persisted/audited; synchronous recompute. | P1 - High | M | Enhance
C24 | Backend API (AIM) | Trend / Causality / Comparison APIs | Heavy analytics endpoints. | Pandas/set math computed on request thread. | Move to background workers; cache results. | CPU-heavy on web thread; no caching. | P2 - Medium | L | Enhance
C25 | Backend API (AIM) | Reports API (PDF/CSV/Excel) | Generate branded PDF, exception CSV/Excel. | fpdf2 + matplotlib; pandas exports inline. | Async report jobs, templated, stored in object storage. | Generated synchronously in-process. | P2 - Medium | M | Enhance
C26 | Backend API (AIM) | Assignments / comments / documents API | Workflow CRUD + evidence upload/download + duplicate check. | SQLite tables; files on local disk. | Managed DB + object storage; signed URLs; audit. | Local disk storage; record indices brittle. | P1 - High | M | Enhance
C27 | Backend API (AIM) | Users API | List users, enable/disable. | SQLite users; toggle endpoint. | Full user lifecycle, provisioning, SSO-synced. | No invite/reset/role-change flows. | P2 - Medium | M | Enhance
C28 | Backend API (AIM) | Custom rules API | Generate/preview/create/update/delete LLM rules. | SQLite custom_rules; in-memory SQLite eval. | Governed rule lifecycle + secure eval sandbox. | Blocklist-only SQL validation; no approval. | P1 - High | L | Enhance
C29 | Backend API (AIM) | CORS / middleware | Cross-origin config. | Env-driven allowlist (AIM); '*' on SQL GPT. | Strict origins, security headers, gateway-level policy. | SQL GPT allows all origins. | P1 - High | S | Enhance
C30 | Backend API (AIM) | App startup hooks | Init DB, create dirs, auto-open browser. | on_startup in main.py; opens localhost browser. | 12-factor startup, health/readiness probes, no desktop assumptions. | Auto-opens browser — not server-appropriate. | P2 - Medium | S | Enhance
C31 | Rule Engine | Scenario rule library | 88 scenarios across ~13 categories with category/description/status/thresholds. | RULES_ENGINE dict in data_loader.py. | Externalize to DB/config, versioned, admin-editable. | Rules hard-coded in source; deploy needed to change. | P1 - High | L | Enhance
C32 | Rule Engine | Breach rule functions | 78 active rule functions + dispatcher producing Breach_Flag/Reason. | @rule decorator registry; pandas logic. | Keep logic; add unit tests, schema contracts, error surfacing. | No tests; per-rule failures only logged/printed. | P1 - High | L | Enhance
C33 | Rule Engine | Hardcoded 'no breach' scenarios | Scenarios intentionally never flagged. | status='hardcoded_no' (11) skipped. | Keep; document rationale + review cadence. | Rationale undocumented. | P3 - Future | S | Existing
C34 | Rule Engine | Excel ingestion / loader | Read workbook, drop stale flags, apply rules, summarize. | load_all_data / reapply_rules (pandas). | Schema validation, column-mapping config, large-file handling. | Assumes exact column names; brittle to schema drift. | P1 - High | M | Enhance
C35 | Rule Engine | Params builder | Build/override threshold params dict. | get_engine_params from RULES_ENGINE. | Persisted, environment-scoped, audited. | Defaults only; overrides not persisted. | P2 - Medium | S | Enhance
C36 | Custom Rules / LLM | NL→SQL WHERE generation | LLM turns plain-English rule into a SQLite WHERE clause + reason. | OpenAI gpt-4o-mini, temp 0, JSON output. | Private/enterprise LLM (e.g. Azure OpenAI), prompt-injection defense, eval tests. | Public OpenAI; no governance/cost control. | P1 - High | L | Enhance
C37 | Custom Rules / LLM | SQL safety validation | Block dangerous SQL before execution. | Keyword blocklist + injection-pattern regex. | Allowlist parser/AST, parameterization, sandbox. | Blocklist is fragile; f-string interpolation. | P1 - High | M | Enhance
C38 | Custom Rules / LLM | In-memory SQLite eval engine | Run validated WHERE against a DataFrame copy. | sqlite3 :memory:; row-index mapping. | Sandboxed, resource-limited, timeouts. | No row/time limits; runs on web thread. | P2 - Medium | M | Enhance
C39 | Persistence (current) | Workflow database | Users, assignments, comments, documents, custom_rules. | SQLite aim_workflow.db (single file). | Managed PostgreSQL, pooled, migrated, backed up. | SQLite — single-writer, no concurrency/HA. | P0 - Critical | L | Enhance
C40 | Persistence (current) | Analytical dataset store | Uploaded breach datasets for analytics. | Held only in process memory (not persisted). | Persist to DB / data lake; partitioned by run/period. | Not persisted at all; lost on restart. | P0 - Critical | L | New
C41 | Persistence (current) | Password hashing | Hash user passwords. | SHA-256 + per-user salt. | bcrypt/argon2 with work factor; pepper. | Fast hash unsuitable for passwords. | P0 - Critical | S | Enhance
C42 | Persistence (current) | Document / file storage | Store evidence + uploads. | Local filesystem (uploads/). | Object storage (S3/Azure Blob) + signed URLs + lifecycle. | Local disk; not durable/shared/scanned. | P1 - High | M | Enhance
C43 | Persistence (current) | Seed / bootstrap data | Default admin account. | Hard-coded admin password seeded in code. | Bootstrap via secret + forced first-login reset. | Hard-coded credentials in source. | P0 - Critical | S | Enhance
C44 | SQL GPT Module | File upload & parsing | Ingest CSV/Excel, clean columns, infer types. | FileParserService (pandas, encoding fallback). | Keep; add validation, size/row caps, async, scan. | Synchronous; minimal validation. | P2 - Medium | M | Enhance
C45 | SQL GPT Module | Table creation & metadata | DataFrame → SQLite table + _metadata registry. | DatabaseService (sqlite3). | Per-tenant schema in managed DB; quotas. | Shared SQLite; relative path quirks (nested dirs). | P1 - High | M | Enhance
C46 | SQL GPT Module | NL→SQL query | Convert question to SELECT and run it. | gpt-4o-mini + QueryExecutor validation. | Governed LLM, allowlist validation, per-tenant isolation. | Public LLM; blocklist; no auth. | P1 - High | M | Enhance
C47 | SQL GPT Module | Query API (tables/schema/delete) | List tables, get schema, delete table. | FastAPI routes under /sql-gpt-api. | AuthN/Z, rate limits, ownership checks. | Unauthenticated; anyone can delete tables. | P0 - Critical | M | Enhance
C48 | SQL GPT Module | Result export (CSV/Excel) | Download query results; server-side re-query for large sets. | download.py streaming responses. | Keep; async for very large; object storage. | Loads full result set in memory. | P3 - Future | S | Existing
C49 | SQL GPT Module | Standalone frontend | Original ES-module chat app + hero animation. | Separate HTML/CSS/JS in SQL GPT/frontend. | Consolidate with embedded version (single codebase). | Two divergent UIs/design systems to maintain. | P2 - Medium | M | Enhance
C50 | Reporting & Export | Branded PDF report | Multi-section executive PDF with charts/tables. | fpdf2 + matplotlib (Agg). | Templated, async, stored, scheduled delivery. | Synchronous; in-process rendering. | P2 - Medium | M | Enhance
C51 | Reporting & Export | Tabular exports | Exception + query results to CSV/Excel. | pandas to_csv / openpyxl writer. | Streamed/async for large; consistent styling. | In-memory build for large sets. | P3 - Future | S | Existing
C52 | Config / Deploy (current) | Local launcher | Start the app locally. | launch.bat → python main.py (port 8001). | Container image + orchestrated deploy. | Desktop/Windows launch assumption. | P1 - High | S | Enhance
C53 | Config / Deploy (current) | Dependencies | Python package requirements. | requirements.txt (some unpinned; differs across the two apps). | Pinned, locked, vuln-scanned (SCA). | Version drift between AIM and SQL GPT. | P2 - Medium | S | Enhance
C54 | Config / Deploy (current) | Secrets / env config | API keys and config. | Plaintext .env files (live OpenAI key on disk). | Secrets manager / vault; no secrets in repo or disk. | Live API key committed to .env on disk. | P0 - Critical | S | Enhance
C55 | Config / Deploy (current) | Cloud deploy descriptor | Deploy config (SQL GPT). | render.yaml (free tier), runtime.txt. | IaC (Terraform) + enterprise hosting. | POC-grade; single service, free tier. | P2 - Medium | M | Enhance

## Chatgpt
Detailed Component and Feature Catalogue
One row per capability. Use filters for domain, priority, phase, owner and effort. This is the principal implementation backlog.
Component ID | Domain | Component | Feature / Capability | Current POC State | Target Production State | Production Gap | Priority | Target Phase | Effort | Primary Owner | Dependencies | Definition of Done / Acceptance Criteria | Notes
PROD-001 | Product & UX | Product governance | Product vision, scope and success metrics | POC scope is implicit in the code and UI. | Approved product charter with measurable control, adoption, accuracy and operational KPIs. | No formal scope, KPI ownership or value measurement. | High | Foundation | M | Product Owner | Business sponsor; Risk; Internal Audit | Signed product charter; KPI definitions; quarterly value review.
PROD-002 | Product & UX | User experience | Role-specific navigation and dashboards | Admin and reviewer screens exist in one SPA. | Role- and permission-aware workspaces for admin, reviewer, approver, auditor, data steward and support. | Roles are coarse and UI hiding is not an authorization control. | High | Foundation | L | Product + Frontend | IAM; authorization model | Every role sees only permitted modules and actions; UX tests pass.
PROD-003 | Product & UX | Accessibility | WCAG accessibility | Basic responsive styling; no accessibility assessment. | WCAG 2.1 AA keyboard, contrast, semantic markup, focus and screen-reader compliance. | No audit, accessibility test suite or remediation backlog. | Medium | Scale | M | Frontend | Design system | Independent accessibility audit has no critical/high findings.
PROD-004 | Product & UX | Design system | Reusable enterprise UI components | Large custom CSS and vanilla JavaScript files. | Versioned design system with reusable forms, tables, charts, notifications and layout components. | Duplicated UI patterns and high maintenance cost. | Medium | Scale | L | Frontend | UX standards | Shared component library adopted across all modules.
PROD-005 | Product & UX | Data tables | Enterprise-scale filtering, sorting and pagination | Some client-side and server-side table controls. | Server-side filtering, stable sorting, pagination, saved views and column preferences. | Inconsistent behavior and potential browser memory issues. | High | MVP | M | Frontend + Backend | Query APIs | Tested with production-scale row counts and response SLAs.
PROD-006 | Product & UX | Notifications | In-app and external notifications | Toast messages only. | Notification center plus email/Teams alerts with templates, preferences, retries and delivery status. | No persistent or actionable alerting. | Medium | Scale | L | Product + Integration | Email/Teams gateway | Assignment/SLA events generate traceable notifications.
PROD-007 | Product & UX | Configuration | Business-admin configuration screens | Thresholds and custom rules can be edited in UI. | Controlled configuration with maker-checker approval, versioning, effective dates and rollback. | Configuration changes take immediate effect without governance. | Critical | MVP | L | Product + Backend | Workflow; audit logging | No production rule change can bypass approval and immutable history.
PROD-008 | Product & UX | Internationalization | Locale, timezone and formatting | Mixed local/UTC date handling and hardcoded text. | Configurable timezone, locale, currency, date and number formats. | Time-sensitive controls can behave differently by server location. | Medium | Scale | M | Frontend + Backend | Enterprise locale policy | Date and amount display/logic is consistent across configured locales.
CCM-001 | CCM Rule Engine | Scenario library | Built-in scenario catalogue | 89 scenarios across 12 categories; 78 active functions and 11 hardcoded no-breach scenarios. | Governed scenario catalogue with owners, risk taxonomy, source mappings, versions and effective dates. | Definitions are embedded in Python and not centrally governed. | Critical | Foundation | XL | Risk Product + Rules Engineering | Control owners; data dictionary | Every scenario has approved metadata, owner, version and traceability.
CCM-002 | CCM Rule Engine | Rule execution | Deterministic breach evaluation | Pandas functions execute in-process against Excel sheets. | Scalable execution engine supporting SQL/Spark/Python with deterministic, replayable runs. | Single-process memory execution cannot support enterprise data volumes. | Critical | MVP | XL | Data Engineering | Data platform; orchestration | Production-volume benchmark meets SLA and reruns reproduce identical output.
CCM-003 | CCM Rule Engine | Rule failure handling | Fail-safe execution and validation | Exceptions are logged and rows remain non-breaches. | Failed rules fail the run or enter an explicit error state; no silent false negatives. | Current exception handling can hide missing columns and logic failures. | Critical | Foundation | M | Rules Engineering | Observability; run status model | Any rule error is visible, alerted and blocks certification.
CCM-004 | CCM Rule Engine | Threshold management | Configurable thresholds | Thresholds are held in memory and edited from UI. | Persisted, typed, effective-dated thresholds by entity/business/unit with approvals. | No persistence, validation, history or environment promotion. | Critical | MVP | L | Rules Engineering | Configuration database | Threshold change history and approvals are queryable and reversible.
CCM-005 | CCM Rule Engine | Custom rules | Natural-language custom rule creation | GPT generates SQLite WHERE clauses and previews matches. | Governed assisted-authoring with templates, validation, test cases, approval and sandbox promotion. | LLM output is only syntactically constrained and can be logically wrong. | High | Scale | XL | AI Engineering + Risk | Model gateway; rule test framework | Custom rules cannot reach production without tests and dual approval.
CCM-006 | CCM Rule Engine | Rule versioning | Version and effective-date management | No formal built-in rule version history. | Immutable versions with draft, approved, active, retired and rollback states. | Cannot reproduce historical outcomes reliably. | Critical | MVP | L | Rules Engineering | Metadata repository | Each breach links to exact rule/threshold/code version.
CCM-007 | CCM Rule Engine | Rule testing | Unit, boundary and regression test cases | No automated scenario-level test suite. | Golden datasets, positive/negative cases, boundary tests and regression baselines for every rule. | Rule changes can silently alter breach outcomes. | Critical | Foundation | XL | QA + Rules Engineering | Representative test data | 100% of production rules have approved automated tests.
CCM-008 | CCM Rule Engine | Rule simulation | What-if and impact analysis | Threshold changes recalculate the uploaded dataset. | Sandbox simulations with before/after impact, population shifts and approval evidence. | Analysis is user-session-specific and not retained. | High | Scale | L | Rules Engineering | Historical data; run repository | Simulation results are retained, comparable and exportable.
CCM-009 | CCM Rule Engine | Explainability | Breach explanation and evidence | Single human-readable reason is added to each row. | Structured explanation showing conditions, evaluated values, thresholds, source lineage and evidence. | Reason text is insufficient for audit defensibility. | High | MVP | L | Rules Engineering | Data lineage | Reviewer can see exactly why each condition passed or failed.
CCM-010 | CCM Rule Engine | Suppression | Exceptions, allowlists and temporary suppressions | Not implemented. | Governed suppression with reason, owner, expiry, approval and reporting. | Operational exceptions cannot be safely managed. | High | Scale | L | Risk Operations | Workflow engine | All suppressions expire or are reapproved and appear in audit reports.
CCM-011 | CCM Rule Engine | Control coverage | Coverage and control mapping | Scenarios are grouped by category. | Map scenarios to risks, regulations, processes, systems, controls and audit assertions. | No enterprise risk/control taxonomy integration. | High | Scale | L | GRC + Product | GRC platform | Coverage gaps and duplicate controls are reportable.
CCM-012 | CCM Rule Engine | Run management | Run IDs, status and certification | Results exist only in user memory after upload. | Persistent scheduled/manual runs with status, counts, errors, certification and rerun lineage. | No durable execution record. | Critical | MVP | XL | Backend + Data Engineering | Run database; orchestration | Every result belongs to an immutable, auditable run.
DATA-001 | Data Platform | File ingestion | CSV and Excel ingestion | Browser upload of CSV/XLS/XLSX; CCM uses multi-sheet Excel. | Managed ingestion with landing zone, schema validation, malware scanning and quarantine. | Entire files are read into memory; backend size limit is not enforced. | Critical | Foundation | L | Data Engineering | Object storage; antivirus | Invalid/malicious files are rejected before processing.
DATA-002 | Data Platform | Database integration | Relational source connectivity | SQLite only. | Approved connectors for Oracle, SQL Server, PostgreSQL, MySQL and enterprise warehouses. | No production source database connectivity. | Critical | MVP | XL | Data Engineering | Network; service accounts; secrets | Parameterized incremental extracts run within agreed SLA.
DATA-003 | Data Platform | Lakehouse integration | Data lake and warehouse connectivity | Not implemented. | S3/ADLS/GCS and Snowflake/Databricks/BigQuery connectors with governed datasets. | Cannot consume enterprise analytical data products. | High | Scale | XL | Data Platform | Cloud platform; catalog | Certified data products are discoverable and ingestible.
DATA-004 | Data Platform | API ingestion | REST/SOAP/event source connectivity | Not implemented. | Secure API and event ingestion for operational systems and near-real-time controls. | Current design is batch-file dependent. | High | Scale | XL | Integration Engineering | API gateway; event bus | Connector retries, idempotency and observability are proven.
DATA-005 | Data Platform | Scheduling | Batch and event orchestration | Manual upload only. | Airflow/ADF/Control-M/Step Functions scheduling with dependencies, retries and calendars. | No unattended CCM operation. | Critical | MVP | XL | Data Engineering | Enterprise scheduler | Runs execute on agreed frequency with automated recovery.
DATA-006 | Data Platform | Incremental processing | CDC and delta loads | Whole file/table loaded each time. | Watermarks, CDC, late-arriving data handling and backfill support. | Full reloads are costly and not scalable. | High | Scale | XL | Data Engineering | Source change tracking | No duplicates or missed records across incremental runs.
DATA-007 | Data Platform | Schema management | Schema registry and contracts | Rules assume exact column names. | Versioned data contracts with compatibility checks and controlled schema evolution. | Schema drift can silently cause failed rules or false negatives. | Critical | Foundation | L | Data Governance | Source owners; catalog | Breaking changes are detected before production execution.
DATA-008 | Data Platform | Data quality | Quality rules and profiling | Basic parser checks; no formal DQ framework. | Completeness, validity, uniqueness, timeliness and reconciliation controls with scorecards. | Bad source data is indistinguishable from control failures. | Critical | MVP | XL | Data Quality | Data contracts; observability | DQ thresholds, ownership and issue workflow are operational.
DATA-009 | Data Platform | Data lineage | End-to-end lineage | Not implemented. | Field-level lineage from source through transformations, rules, breaches and reports. | Audit cannot trace output to source data. | Critical | Scale | XL | Data Governance | Metadata catalog | A breach can be traced to source system, extract and transformation.
DATA-010 | Data Platform | Reference data | Master/reference data management | Thresholds and labels are code-based. | Governed reference datasets for products, branches, users, limits, MCCs, risk ratings and calendars. | No central reference data lifecycle. | High | Scale | L | Data Governance | MDM platform | Reference changes are versioned and propagated consistently.
DATA-011 | Data Platform | Persistent results | Breach and run repository | CCM output is stored in process memory. | Normalized production database for runs, populations, breaches, evidence, assignments and outcomes. | Results disappear on restart and cannot be shared between workers. | Critical | MVP | XL | Backend + DBA | PostgreSQL/SQL Server; data model | Results survive restart, support concurrency and retain history.
DATA-012 | Data Platform | Object storage | Files and evidence storage | Uploads are stored on local disk. | Encrypted object storage with lifecycle, retention, malware scanning and signed downloads. | Local paths are fragile; one stored path already points to an obsolete directory. | Critical | MVP | L | Platform Engineering | S3/ADLS; key management | Files remain available across deployments and are access-controlled.
DATA-013 | Data Platform | Archival | Retention and purge | No formal retention process. | Policy-driven archival, legal hold and defensible deletion for data, evidence and logs. | Data may be retained indefinitely. | High | Scale | L | Records Management | Legal; security; object storage | Automated retention jobs and exception reports are approved.
DATA-014 | Data Platform | Reconciliation | Source-to-target control totals | Record counts are displayed but not reconciled. | Automated control totals, hash totals, duplicate checks and source acknowledgements. | Completeness of ingestion is not proven. | Critical | MVP | L | Data Engineering | Source extracts | Every run has passed reconciliation evidence.
DATA-015 | Data Platform | Data privacy | Masking and minimization | Uploaded datasets and PDFs may contain personal information. | Field classification, masking, tokenization, minimization and purpose limitation. | Sensitive information is exposed to broad application functions. | Critical | Foundation | XL | Privacy + Data Security | Data catalog; IAM | Sensitive fields are classified and masked by role/environment.
WF-001 | Case Management | Assignments | Breach assignment workflow | Admin assigns selected record indices to reviewers. | Case creation by stable breach IDs with queues, ownership, bulk assignment and reassignment. | Displayed row indices can change after sorting and are not durable identifiers. | Critical | MVP | XL | Workflow Engineering | Breach repository | Assignments always reference immutable breach IDs.
WF-002 | Case Management | Statuses | Case lifecycle | Pending, In Review and Resolved. | Configurable lifecycle including triage, investigation, remediation, validation, closure and reopen. | Workflow is too simple for controlled operations. | High | MVP | L | Risk Operations | Workflow engine | State transitions are role-controlled and audited.
WF-003 | Case Management | SLA | SLA and aging management | Not implemented. | Priority-based SLA timers, business calendars, reminders, escalation and breach reporting. | No timeliness governance. | High | MVP | L | Risk Operations | Notification service; calendars | Overdue cases trigger escalation and dashboard reporting.
WF-004 | Case Management | Evidence | Evidence upload and management | Documents are uploaded to local disk. | Versioned evidence repository with metadata, virus scan, access control and retention. | No content controls or durable storage. | Critical | MVP | L | Workflow + Platform | Object storage | Evidence downloads require authorization and are immutable.
WF-005 | Case Management | Collaboration | Comments and activity timeline | Basic comments table. | Unified immutable timeline for comments, status, assignment, evidence and approvals. | Events are spread across tables and lack comprehensive history. | High | MVP | M | Workflow Engineering | Audit event model | All case actions appear chronologically with actor and timestamp.
WF-006 | Case Management | Duplicate handling | Duplicate and related case management | Checks overlapping row indices for a scenario. | Entity- and breach-ID-based duplicate detection, merge/link and parent-child cases. | Index-based duplicates are unreliable. | Medium | Scale | L | Workflow Engineering | Entity resolution | Duplicate cases are detected with explainable matching.
WF-007 | Case Management | Disposition | Outcome and root-cause capture | Only status and notes. | Structured disposition, false-positive reason, root cause, remediation and financial/regulatory impact. | No outcome analytics or model feedback. | High | MVP | L | Risk Operations | Taxonomy; reporting | Mandatory closure fields support management reporting.
WF-008 | Case Management | Approvals | Maker-checker and closure validation | Not enforced. | Independent approval for critical cases, rule changes, suppressions and closure. | Single user can perform sensitive lifecycle actions. | Critical | MVP | L | Workflow Engineering | RBAC | Configured segregation-of-duties rules cannot be bypassed.
WF-009 | Case Management | Search | Global case and breach search | Page-level search only. | Indexed global search across cases, entities, scenarios, evidence metadata and comments. | Investigators cannot efficiently retrieve related history. | Medium | Scale | L | Backend | Search engine | Search meets relevance and response-time targets.
WF-010 | Case Management | External integration | GRC/ticketing case synchronization | Not implemented. | Bidirectional integration with ServiceNow/Jira/Archer/MetricStream as required. | Cases are isolated from enterprise remediation processes. | High | Scale | XL | Integration Engineering | GRC/ticketing APIs | Case IDs, status and evidence synchronize without duplication.
AN-001 | Analytics & Reporting | Executive dashboard | Portfolio KPIs and category analysis | KPIs, heatmaps, charts and treemap in Plotly. | Certified metrics, saved filters, drill-through and period comparisons backed by persistent data. | Metrics are session-based and not formally governed. | High | MVP | L | BI + Product | Semantic layer | Dashboard metrics reconcile to certified report totals.
AN-002 | Analytics & Reporting | Scenario drill-down | Record-level analysis | Pagination, search, filters and reason breakdown. | Secure drill-down with stable IDs, lineage, evidence and case links. | No row-level security or durable linkage. | Critical | MVP | L | Backend + Frontend | Authorization; breach repository | Users only see permitted records and can trace each result.
AN-003 | Analytics & Reporting | Trend analysis | Time-series monitoring | Heuristically selects the first likely date column. | Scenario-specific governed time dimensions and certified trend logic. | Automatic date selection can produce misleading trends. | High | Scale | L | BI + Rules Engineering | Scenario metadata | Each trend uses an approved date field and period definition.
AN-004 | Analytics & Reporting | Causality analysis | Cross-scenario entity overlap | Jaccard, co-occurrence and influence calculations. | Validated network/entity analytics with confidence, data sufficiency and explainability. | Current output suggests causality from simple association. | High | Scale | XL | Data Science + Risk | Entity resolution | Terminology and methodology are independently validated.
AN-005 | Analytics & Reporting | Comparison mode | Period/file comparison | Compares two uploaded workbooks. | Persistent run-to-run comparison with normalized populations and explainable deltas. | Comparability and population changes are not controlled. | High | Scale | L | BI + Backend | Run repository | Deltas separate source-population, rule and threshold effects.
AN-006 | Analytics & Reporting | Exception reporting | Filtered breach export | Preview plus CSV/Excel exports. | Asynchronous governed exports with filter fidelity, masking, watermarking and audit logs. | Current downloads do not pass UI filters and can export different data. | Critical | MVP | L | Backend | Export service; authorization | Downloaded files exactly match filters and access rights.
AN-007 | Analytics & Reporting | PDF reporting | Management PDF report | Generated synchronously with matplotlib and fpdf2. | Template-managed, branded, asynchronous reports with versioned metric definitions. | Large reports can block API workers and lack distribution controls. | Medium | Scale | L | Reporting Engineering | Job queue; object storage | Reports are generated in background and retained with metadata.
AN-008 | Analytics & Reporting | BI integration | Enterprise reporting platform | Custom web charts only. | Published semantic model for Power BI/Tableau/Qlik and regulatory reporting. | Analytics cannot be reused across enterprise reporting. | Medium | Scale | XL | BI Team | Data warehouse | Certified datasets are available to approved BI tools.
AN-009 | Analytics & Reporting | Metric governance | Business glossary and metric certification | Definitions exist in code descriptions. | Named metric owners, formulas, lineage, quality checks and certification status. | Same metric could be interpreted differently. | High | Foundation | M | Data Governance | Catalog; business owners | All executive metrics have approved definitions.
AN-010 | Analytics & Reporting | Scheduled distribution | Scheduled reports and subscriptions | Manual downloads. | Scheduled secure delivery with recipient groups, expiry and delivery audit. | No recurring reporting capability. | Medium | Scale | L | Reporting Engineering | Notification service | Approved users can subscribe to governed reports.
AI-001 | AI / SQL GPT | Natural-language query | Text-to-SQL generation | OpenAI gpt-4o-mini creates SQLite SELECT queries. | Enterprise model gateway with approved models, policy controls, prompt versions and evaluation. | Direct API dependency and model configuration in source. | High | Scale | XL | AI Platform | Model gateway; legal approval | All calls use approved gateway and are traceable to prompt/model versions.
AI-002 | AI / SQL GPT | Prompt data protection | Schema and sample-data handling | Schema and up to three sample rows are sent to OpenAI. | Data minimization, redaction, classification checks and no sensitive row samples by default. | README understates third-party data sharing. | Critical | Foundation | L | AI Security + Privacy | DLP; model contract | No restricted data leaves approved boundary; consent and notices are accurate.
AI-003 | AI / SQL GPT | Query safety | Read-only SQL enforcement | Basic keyword and pattern validation for query endpoint. | AST-based SQL policy engine, read-only DB account, statement timeout, row/byte limits and allowlisted schemas. | String validation can be bypassed and lacks resource controls. | Critical | MVP | XL | AI Platform + DBA | SQL parser; database roles | Adversarial query suite cannot read unauthorized data or mutate state.
AI-004 | AI / SQL GPT | Download query safety | Safe export execution | Download endpoint directly executes client-supplied SQL. | Exports reference server-side query IDs; SQL is never trusted from browser payload. | Validation is bypassed during download. | Critical | Foundation | M | Backend | Query result store | Download cannot execute arbitrary client SQL.
AI-005 | AI / SQL GPT | Result limits | Query pagination and resource governance | Fetches all query results into process memory. | Default LIMIT, pagination, cost estimation, cancellation, quotas and asynchronous large exports. | Large queries can exhaust memory or workers. | Critical | MVP | L | Backend + DBA | Job queue | Load test proves bounded memory and response times.
AI-006 | AI / SQL GPT | Model evaluation | Accuracy and safety benchmark | No automated LLM evaluation. | Curated question-SQL benchmark, execution accuracy, safety, hallucination and regression evaluation. | No evidence of query correctness. | High | Foundation | XL | AI Engineering + QA | Representative schemas | Release gates meet agreed accuracy and safety thresholds.
AI-007 | AI / SQL GPT | Human confirmation | Review generated SQL | SQL is displayed after execution. | Risk-based confirmation before execution, especially for costly/sensitive queries. | User cannot validate SQL before it runs. | High | MVP | M | Product + Frontend | Query classification | Sensitive/high-cost queries require explicit confirmation.
AI-008 | AI / SQL GPT | Feedback | User feedback and correction loop | Not implemented. | Capture helpful/not-helpful, corrected SQL and failure reason for evaluation and improvement. | No structured learning signal. | Medium | Scale | M | AI Product | Evaluation store | Feedback is measurable and linked to prompt/model versions.
AI-009 | AI / SQL GPT | Model observability | Token, latency, error and cost monitoring | No AI-specific metrics. | Per-request model, tokens, latency, cost, policy decision and outcome telemetry. | Cost and quality cannot be managed. | High | MVP | L | AI Platform | Observability stack | Dashboards and budgets cover all model usage.
AI-010 | AI / SQL GPT | Fallback | Model/provider resilience | Single model/provider. | Configured fallback model, circuit breaker, retry policy and graceful non-AI mode. | Provider failure disables functionality. | Medium | Scale | L | AI Platform | Secondary model/provider | Failure drills demonstrate controlled fallback.
SEC-001 | Security & IAM | Authentication | Enterprise SSO | Local username/password and JWT. | OIDC/SAML SSO with corporate IdP, MFA and conditional access. | Standalone credentials create security and lifecycle risk. | Critical | Foundation | XL | IAM | Azure AD/Okta/Ping | All production users authenticate through enterprise IdP.
SEC-002 | Security & IAM | Password security | Credential storage | Salted single-round SHA-256 and hardcoded default admin credential. | No local password where SSO applies; otherwise Argon2id/bcrypt and controlled bootstrap. | Current password hashing and seed credential are insecure. | Critical | Foundation | M | Security Engineering | IAM | Hardcoded credentials removed and existing credentials rotated.
SEC-003 | Security & IAM | Token security | Session and JWT management | 24-hour JWT with a default fallback secret. | Short-lived access tokens, refresh/revocation, key rotation and secure cookies or approved token storage. | Default secret and sessionStorage token increase compromise impact. | Critical | Foundation | L | Security Engineering | IdP; key management | Token theft/revocation scenarios pass security testing.
SEC-004 | Security & IAM | Authorization | RBAC/ABAC enforcement | Most CCM routes require authentication; many mutations are not admin/owner restricted. | Central policy-based authorization for module, action, data domain, region and case ownership. | Reviewers can modify users and other users' assignments/documents. | Critical | Foundation | XL | Security + Backend | Role model; policy engine | Automated authorization matrix tests cover every endpoint.
SEC-005 | Security & IAM | SQL GPT access | Protect integrated SQL GPT routes | All /sql-gpt-api routes are unauthenticated. | SSO, permission checks, dataset entitlements, quotas and audit logging. | Anyone with network access can query, upload and delete tables. | Critical | Foundation | L | Backend + Security | IAM | Anonymous access is impossible and destructive actions are restricted.
SEC-006 | Security & IAM | Row-level security | Data entitlements | Not implemented. | Row/column-level security based on business unit, geography, customer class and sensitivity. | All authenticated users can see broad data. | Critical | MVP | XL | Data Security | Entitlement source | RLS/CLS tests prove no cross-boundary access.
SEC-007 | Security & IAM | Secrets | Secrets and key management | OpenAI key in local .env; JWT has fallback. | Vault/Key Vault/Secrets Manager with rotation, least privilege and no secrets in files/images. | Local secret handling is unsuitable for production. | Critical | Foundation | L | Platform Security | Enterprise vault | Secret scanning is clean and rotations are automated.
SEC-008 | Security & IAM | Encryption | Encryption in transit and at rest | Local HTTP and unencrypted local SQLite/files. | TLS 1.2+, encrypted databases/object storage/backups and managed keys. | Sensitive control and personal data lacks enterprise encryption controls. | Critical | Foundation | L | Platform Security | PKI; KMS | Encryption configuration passes security review.
SEC-009 | Security & IAM | File security | Upload validation and malware protection | Extension checks only; no enforced backend size limit. | MIME/content validation, antivirus, archive controls, file limits and quarantine. | Malicious or oversized files can be processed. | Critical | Foundation | L | Application Security | Malware scanning service | Security test corpus is rejected safely.
SEC-010 | Security & IAM | Audit trail | Immutable security and business audit logging | Created/updated timestamps and comments exist; no complete event log. | Immutable actor/action/resource/before-after audit events forwarded to SIEM. | Sensitive changes and data access are not fully traceable. | Critical | MVP | XL | Security + Backend | SIEM; event schema | Audit can reconstruct rule, case, user and export activity.
SEC-011 | Security & IAM | Application security | Secure SDLC and vulnerability management | No evidence of SAST/DAST/dependency scanning. | Threat modeling, SAST, SCA, DAST, container scanning and remediation SLAs. | Security defects are not systematically identified. | Critical | Foundation | L | AppSec | CI/CD | No open critical/high findings at production release.
SEC-012 | Security & IAM | Network security | Private connectivity and segmentation | Local application; broad CORS in standalone SQL GPT. | Private subnets/endpoints, WAF/API gateway, restricted egress and explicit CORS. | No production network trust boundaries. | High | MVP | XL | Network Security | Cloud/network platform | Only approved paths can reach app, databases and model gateway.
SEC-013 | Security & IAM | Privacy | Consent, notices and subject rights | Evidence PDF contains personal and employment data. | Privacy assessment, processing register, notices, access controls and deletion workflows. | No formal privacy controls around uploaded evidence. | Critical | Foundation | XL | Privacy Office | Legal; records management | DPIA/PIA approved and privacy controls tested.
SEC-014 | Security & IAM | Security testing | Penetration and adversarial testing | Not performed. | Pen test, API abuse, authorization, file upload, SQL and LLM red-team testing. | Production exposure is unassessed. | Critical | Pre-Go-Live | L | AppSec | Stable production candidate | All critical/high issues remediated or formally accepted.
ARCH-001 | Architecture & Platform | Application architecture | Modular service boundaries | Single FastAPI process embeds CCM and SQL GPT. | Modular monolith or services with clear domains, contracts and independent scaling where needed. | Tight coupling and import-path manipulation complicate deployment. | High | Foundation | XL | Solution Architecture | Target architecture decision | Approved architecture and interface contracts.
ARCH-002 | Architecture & Platform | API design | Versioned API contracts | Unversioned REST routes and mixed response conventions. | Versioned OpenAPI contracts, standard errors, idempotency and backward compatibility. | Clients are tightly coupled to implementation. | High | MVP | L | Backend Architecture | API gateway | Contract tests protect supported API versions.
ARCH-003 | Architecture & Platform | Database architecture | Production relational database | Multiple SQLite files with working-directory-dependent paths. | Managed PostgreSQL/SQL Server with migrations, pooling, HA, backups and read replicas if required. | SQLite and ambiguous paths do not support concurrency/HA. | Critical | Foundation | XL | DBA + Backend | Cloud/on-prem database service | Concurrent load, failover and recovery tests pass.
ARCH-004 | Architecture & Platform | Background jobs | Asynchronous processing | Uploads, rules, exports and PDFs run in API workers. | Queue-based workers for ingestion, rule runs, reports, notifications and large exports. | Long jobs can block requests and be lost on restart. | Critical | MVP | XL | Platform Engineering | RabbitMQ/Kafka/SQS; workers | Jobs are retryable, observable and idempotent.
ARCH-005 | Architecture & Platform | Caching | Distributed cache | Browser page cache and in-process state. | Redis or approved cache for sessions, metadata and safe query/result caching. | In-process state is not shared across replicas. | High | MVP | L | Platform Engineering | Redis | Multiple replicas show consistent user state.
ARCH-006 | Architecture & Platform | Containerization | Immutable deployment artifacts | Launched by batch file or Python. | Hardened container images, non-root runtime and reproducible builds. | Environment setup is manual and mutable. | Critical | Foundation | L | DevOps | Container registry | Image builds are reproducible and pass scans.
ARCH-007 | Architecture & Platform | Orchestration | Kubernetes/PaaS deployment | Local server and legacy Render configuration for nested app. | Enterprise Kubernetes/OpenShift/App Service/ECS deployment with autoscaling and health probes. | No resilient production runtime. | Critical | MVP | XL | Platform Engineering | Hosting decision | Deployment survives instance loss and scales under load.
ARCH-008 | Architecture & Platform | Configuration | Environment-specific configuration | Paths, model and some defaults are hardcoded. | Typed centralized configuration with dev/test/UAT/prod separation and validation. | Configuration drift and unsafe defaults. | Critical | Foundation | L | Backend + DevOps | Secrets and config store | Startup fails fast when required config is missing.
ARCH-009 | Architecture & Platform | Resilience | Timeouts, retries and circuit breakers | Limited exception handling; no standardized resilience policies. | Service-specific timeouts, bounded retries, circuit breakers and graceful degradation. | External failures can hang or cascade. | High | MVP | L | Platform Engineering | HTTP/database clients | Failure injection tests demonstrate controlled behavior.
ARCH-010 | Architecture & Platform | Multi-tenancy | Business-unit/data-domain isolation | Per-user in-memory CCM uploads; global SQL GPT tables. | Explicit tenant/domain model with isolated data, configuration, quotas and administration. | Current isolation semantics are inconsistent. | High | Scale | XL | Solution Architecture | IAM; data model | Isolation tests prove no tenant/domain leakage.
ARCH-011 | Architecture & Platform | Feature management | Feature flags | Not implemented. | Controlled rollout, kill switches and cohort-based activation. | Risky features cannot be disabled independently. | Medium | MVP | M | DevOps + Product | Feature flag platform | Critical features can be disabled without redeployment.
ARCH-012 | Architecture & Platform | Dependency management | Pinned and maintained dependencies | Main requirements are unpinned; nested requirements are old and separately managed. | Single dependency strategy, lock files, update automation and compatibility testing. | Builds are not fully reproducible and vulnerability drift is likely. | High | Foundation | M | DevOps | Package repository | Rebuild produces identical dependency set.
OPS-001 | DevSecOps & SRE | Source control | Repository and branching governance | Nested Git repository and parent workspace are inconsistent. | Single governed repository strategy, protected branches, CODEOWNERS and review rules. | Nested repo complicates versioning and releases. | High | Foundation | M | Engineering Lead | Repository migration | All deployable code is traceable to one release commit.
OPS-002 | DevSecOps & SRE | CI/CD | Automated build, test and deploy | No pipeline present. | Pipeline with lint, tests, security scans, artifact signing, migrations and promotion approvals. | Manual releases are error-prone. | Critical | Foundation | XL | DevOps | Test suite; registry | Every deployment is automated and auditable.
OPS-003 | DevSecOps & SRE | Environment strategy | Dev, test, UAT, pre-prod and prod | Single local workspace. | Isolated environments with controlled data and configuration promotion. | No representative validation path. | Critical | Foundation | XL | DevOps | Infrastructure capacity | Release passes defined gates in each environment.
OPS-004 | DevSecOps & SRE | Infrastructure as code | Reproducible infrastructure | Not implemented. | Terraform/Bicep/CloudFormation/Helm for network, compute, storage, databases and monitoring. | Infrastructure cannot be reproduced or reviewed. | Critical | Foundation | XL | Platform Engineering | Target hosting | Environment can be recreated from versioned code.
OPS-005 | DevSecOps & SRE | Logging | Structured application logging | Print statements and framework logs. | Structured correlation-aware logs with redaction, levels and centralized retention. | Troubleshooting and audit are weak. | Critical | MVP | L | Backend + SRE | Logging platform | Requests, jobs and rule runs share correlation IDs.
OPS-006 | DevSecOps & SRE | Metrics | Technical and business metrics | No operational metrics. | Latency, error, saturation, queue, DB, model, run and breach pipeline metrics. | Health and capacity are invisible. | Critical | MVP | L | SRE | Prometheus/App Insights/CloudWatch | Dashboards cover agreed golden signals and business SLIs.
OPS-007 | DevSecOps & SRE | Tracing | Distributed tracing | Not implemented. | OpenTelemetry traces across API, jobs, DB, source connectors and model calls. | Cross-component latency cannot be diagnosed. | Medium | Scale | L | SRE | Telemetry collector | Sampled traces support end-to-end diagnosis.
OPS-008 | DevSecOps & SRE | Alerting | Actionable production alerts | No production alerting. | SLO-, security- and data-quality-based alerts with routing, deduplication and runbooks. | Failures require user discovery. | Critical | MVP | L | SRE | On-call platform | Alerts have owners, thresholds and tested runbooks.
OPS-009 | DevSecOps & SRE | Health checks | Readiness, liveness and dependency health | Standalone SQL GPT has a basic health endpoint; integrated app lacks dependency-aware checks. | Readiness/liveness plus DB, queue, object store and model-gateway checks. | Orchestrator cannot distinguish ready from unhealthy. | High | MVP | M | Backend + SRE | Deployment platform | Traffic is removed automatically from unhealthy instances.
OPS-010 | DevSecOps & SRE | SLOs | Service levels and error budgets | No formal availability or performance objectives. | Approved SLOs for UI/API, runs, alerts, exports and recovery. | Production expectations are undefined. | High | Foundation | M | Product + SRE | Business criticality assessment | SLIs and error budgets are reported monthly.
OPS-011 | DevSecOps & SRE | Backup and recovery | Backup, restore and point-in-time recovery | Local files and SQLite databases only. | Automated encrypted backups, PITR, restore tests and documented RPO/RTO. | Data can be lost with host failure. | Critical | MVP | L | DBA + SRE | Managed database; object storage | Restore drill meets approved RPO/RTO.
OPS-012 | DevSecOps & SRE | Disaster recovery | Regional/site recovery | Not implemented. | DR architecture, replication, failover procedures and annual exercises. | No continuity capability. | High | Scale | XL | BCP/DR + SRE | Business impact analysis | DR exercise meets recovery objectives.
OPS-013 | DevSecOps & SRE | Capacity | Performance and capacity management | No benchmark beyond small POC datasets. | Load, stress, soak and volume tests with forecasts and autoscaling thresholds. | Unknown production limits. | Critical | Pre-Go-Live | XL | Performance Engineering | Production-like environment | Peak and growth volumes meet SLA with headroom.
OPS-014 | DevSecOps & SRE | Runbooks | Operational support procedures | Launch batch file only. | Runbooks for incidents, failed runs, reprocessing, key rotation, recovery and escalation. | Support depends on developer knowledge. | High | Pre-Go-Live | L | SRE + Support | Observability; support model | Support team completes operational readiness exercise.
QA-001 | Quality Engineering | Unit testing | Backend and rule unit tests | No test files in repository. | Automated tests for services, validation, authorization, calculations and edge cases. | Regression risk is high. | Critical | Foundation | XL | QA + Engineering | Test framework | Coverage threshold and critical-path tests enforced in CI.
QA-002 | Quality Engineering | API testing | Contract and integration tests | No automated API tests. | OpenAPI contract, database, object storage, IdP and external-system integration tests. | Route and integration failures are detected manually. | Critical | Foundation | XL | QA | Test environments | All supported APIs have positive, negative and authorization tests.
QA-003 | Quality Engineering | UI testing | Automated browser tests | No frontend tests. | Critical user journeys automated across supported browsers and accessibility modes. | Large SPA can regress without detection. | High | MVP | L | QA | Stable selectors; test data | Login, upload, analysis, rule and case workflows pass automatically.
QA-004 | Quality Engineering | Data testing | Data pipeline and reconciliation tests | Manual workbook validation. | Automated schema, DQ, reconciliation and transformation tests. | Data defects can invalidate controls. | Critical | MVP | XL | Data QA | Data contracts | Failed data tests prevent run certification.
QA-005 | Quality Engineering | UAT | Business acceptance | POC demonstrations only. | Documented UAT scenarios, expected results, defect triage and formal sign-off. | Business readiness is not evidenced. | Critical | Pre-Go-Live | L | Product + Business QA | UAT environment | Control owners sign off all critical journeys and outputs.
QA-006 | Quality Engineering | Regression | Golden-result comparison | Current workbook can serve as ad hoc reference. | Versioned golden datasets and expected breach counts at scenario and record level. | No automatic detection of calculation changes. | Critical | Foundation | L | Rules QA | Approved expected results | Every release compares outputs and explains approved deltas.
QA-007 | Quality Engineering | Security QA | Automated abuse and authorization tests | Not implemented. | Endpoint permission matrix, OWASP tests, upload attacks and SQL/LLM adversarial cases. | Known authorization gaps are not guarded against regression. | Critical | Foundation | XL | AppSec + QA | Security requirements | Security test suite is mandatory in CI.
QA-008 | Quality Engineering | Release management | Release evidence and rollback | No release process. | Release notes, approvals, evidence bundle, database migration strategy and tested rollback. | Changes cannot be safely promoted or reversed. | Critical | MVP | L | Release Manager | CI/CD | Every release has traceable approvals and rollback plan.
GOV-001 | Governance & Operations | Model governance | AI model risk management | No formal model governance. | Use-case classification, model inventory, validation, monitoring and change approval. | LLM functionality may fall under enterprise model-risk policy. | High | Foundation | XL | Model Risk | AI policy; legal | Model governance approval is obtained before production.
GOV-002 | Governance & Operations | Control governance | Control owner attestation | Scenario descriptions exist in code. | Named control owners periodically attest design, thresholds, data and performance. | No recurring control certification. | High | Scale | L | Risk Governance | GRC platform | Attestations and overdue reviews are tracked.
GOV-003 | Governance & Operations | Change management | Production change control | Direct code/config changes. | Risk-based change tickets, approvals, segregation, testing and emergency process. | No controlled production change lifecycle. | Critical | Foundation | L | Change Manager | ITSM | All production changes have approved records and evidence.
GOV-004 | Governance & Operations | Audit readiness | Evidence package | Reports and some timestamps are available. | Automated evidence package covering data, rule version, run, approvals, cases and access logs. | Audit evidence must be manually assembled. | High | Scale | L | Compliance + Product | Audit repository | Sample audit request can be fulfilled within agreed time.
GOV-005 | Governance & Operations | Support model | L1/L2/L3 support | Developer-operated POC. | Defined service ownership, support tiers, hours, SLAs, escalation and knowledge base. | No sustainable operating model. | Critical | Pre-Go-Live | L | Service Owner | Operations staffing | Support acceptance and knowledge transfer completed.
GOV-006 | Governance & Operations | Training | User and administrator training | No formal training materials. | Role-based training, quick reference, admin guide and release communications. | Adoption and controlled usage are at risk. | Medium | Pre-Go-Live | M | Product + Training | Final workflows | Target users complete training and competency checks.
GOV-007 | Governance & Operations | Documentation | Technical and operational documentation | Nested SQL GPT README; limited CCM documentation. | Architecture, API, data model, runbook, rule catalogue, security and user documentation. | Knowledge is concentrated in code. | High | MVP | L | Engineering | Final design | Documentation is reviewed and versioned with releases.
GOV-008 | Governance & Operations | Licensing | Software and model licensing review | Open-source packages and external model API used. | Approved license inventory, SBOM, commercial terms and usage restrictions. | Legal/licensing obligations are not documented. | High | Foundation | M | Legal + Procurement | SBOM; contracts | All dependencies and services have approved usage terms.
GOV-009 | Governance & Operations | FinOps | Cost model and budgets | No cost tracking. | Compute, storage, database, model and support cost forecasts with budgets and chargeback. | Operating cost is unknown. | Medium | Scale | L | FinOps + Product | Architecture and usage estimates | Monthly cost dashboard and budget alerts are active.
GOV-010 | Governance & Operations | Decommissioning | Legacy and POC retirement | POC databases, keys and evidence remain in local workspace. | Controlled migration, archival, credential rotation and secure POC decommissioning. | Residual data and secrets create ongoing risk. | Critical | Pre-Go-Live | M | Service Owner + Security | Production cutover | POC data/secrets are securely removed after approved migration.