## Project Plan
SSG NF — FX / OTC Settlement Compare & Match · Pilot Runbook & Project Plan
Reverse-planned to Pilot-Ready on 14-Aug-2026 · window 1-Jul → 14-Aug-2026 · PROPOSED — for review
ID | Phase | Workstream | Task | Owner | Start | End | Days | Status | Notes
1 | 0 · Governance & PMO | PMO | Daily stand-up across workstreams | Sabre / Protiviti | 2026-07-01 | 2026-08-14 | 33 | In Progress | 15-min sync; surface blockers & dependencies
2 | 0 · Governance & PMO | PMO | Weekly steering committee + status pack | Sabre | 2026-07-01 | 2026-08-14 | 33 | In Progress | RAG status, milestones, risks
3 | 0 · Governance & PMO | PMO | RAID log (risks / assumptions / issues / deps) | Protiviti | 2026-07-01 | 2026-08-14 | 33 | In Progress | Live log; reviewed weekly
4 | 0 · Governance & PMO | Decision | Tool / vendor selection — ServiceNow vs AWS vs Internal | Sabre + IT | 2026-07-15 | 2026-07-18 | 3 | Planned | GATE: converge to one solution for the pilot
5 | 0 · Governance & PMO | Decision | Go / No-Go for pilot | Sabre + IT + Ops | 2026-08-13 | 2026-08-13 | 1 | Planned | Entry: UAT signed-off + approvals complete
6 | 1 · Requirements & Design | Requirements | FSD finalised | IT team | 2026-06-26 | 2026-06-26 | 1 | Done
7 | 1 · Requirements & Design | Requirements | BRD sign-off | Ops + Sabre | 2026-06-30 | 2026-07-01 | 2 | Done
8 | 1 · Requirements & Design | Requirements | Jira stories with success criteria | Sabre | 2026-06-26 | 2026-07-01 | 4 | Done | Backlog groomed
9 | 1 · Requirements & Design | Requirements | UI/UX wireframes — Portal, Dashboard, Trade Detail, Compare & Match | Protiviti | 2026-07-01 | 2026-07-04 | 3 | Done | Editable wireframe decks delivered
10 | 1 · Requirements & Design | Requirements | Onboarding Wizard functional spec | Sabre / Athira | 2026-07-01 | 2026-07-08 | 6 | In Progress | Haris to brief Athira (per 25-Jun)
11 | 1 · Requirements & Design | Requirements | Analyst / Manager / Admin functional specs | Protiviti | 2026-07-04 | 2026-07-09 | 4 | In Progress | Aligned to wireframes
12 | 1 · Requirements & Design | Design | Architecture diagram (candidate + target-state) | All workstreams | 2026-07-07 | 2026-07-10 | 4 | Planned | Per workstream + selected solution
13 | 1 · Requirements & Design | Design | Data model & field definitions (trade / allege / golden) | All workstreams | 2026-07-07 | 2026-07-11 | 4 | Planned | Canonical schema
14 | 1 · Requirements & Design | Design | Integration design — Graph API, Gloss API, target systems | IT + Protiviti | 2026-07-08 | 2026-07-11 | 3 | Planned | Auth, endpoints, write-back
15 | 2 · Environment & Access | Access | Laptops & IAC for Protiviti | IT team | 2026-06-26 | 2026-06-26 | 1 | Done
16 | 2 · Environment & Access | Access | SNOW developer accesses (Name & Forms) | Sabre | 2026-07-01 | 2026-07-04 | 3 | In Progress
17 | 2 · Environment & Access | Access | ServiceNow instance creation (eval) | IT team | 2026-07-01 | 2026-07-03 | 3 | In Progress
18 | 2 · Environment & Access | Access | Access to eval instance | Brett / Snow team | 2026-07-02 | 2026-07-04 | 2 | In Progress
19 | 2 · Environment & Access | Approvals | API access | Santosh | 2026-07-02 | 2026-07-02 | 1 | Done
20 | 2 · Environment & Access | Approvals | NTI approval (new-tech / Graph API) | NTI team / IT | 2026-07-03 | 2026-07-11 | 6 | At Risk | Can take weeks — critical-path risk; start early
21 | 2 · Environment & Access | Infra | dev / qa / uat environment creation | IT team | 2026-07-03 | 2026-07-09 | 5 | In Progress
22 | 2 · Environment & Access | Dev | Repository creation + branching strategy | All workstreams | 2026-07-03 | 2026-07-04 | 1 | In Progress
23 | 2 · Environment & Access | Dev | Code migration (AWS + Protiviti native app) | NTI / IT team | 2026-07-02 | 2026-07-08 | 5 | In Progress | Lift existing PoC code
24 | 2 · Environment & Access | Infra | CI/CD pipeline scaffolding | IT + Protiviti | 2026-07-08 | 2026-07-14 | 5 | Planned
25 | 2 · Environment & Access | Infra | Hosting decision for selected PoC solution | Sabre + IT | 2026-07-08 | 2026-07-17 | 8 | Planned | Where selected vendor solution is hosted
26 | 2 · Environment & Access | Approvals | AWS tenant creation | Sabre + BMO | 2026-07-07 | 2026-07-14 | 6 | Planned
27 | 2 · Environment & Access | Approvals | HR IDs for AWS resources | IT team | 2026-07-07 | 2026-07-14 | 6 | Planned
28 | 3 · Data | Data | Synthetic data samples v1 (partial) | IT / Protiviti | 2026-06-26 | 2026-07-04 | 6 | In Progress | Start PoC on partial; full set in 1–2 wks
29 | 3 · Data | Data | Test data annotation | Ops + Sabre | 2026-06-26 | 2026-06-26 | 1 | Done
30 | 3 · Data | Data | Golden source / bank-booked reference (Gloss extract) | Ops + IT | 2026-07-07 | 2026-07-14 | 6 | Planned | Reference for Compare & Match
31 | 3 · Data | Data | Full synthetic + masked production-like dataset | IT / Ops | 2026-07-07 | 2026-07-18 | 9 | Planned
32 | 3 · Data | Data | UAT test dataset | Ops + Protiviti | 2026-07-21 | 2026-07-28 | 6 | Planned
33 | 4 · Build — Foundations | Development | Core tables / schema + RBAC scaffold | All workstreams | 2026-07-07 | 2026-07-11 | 4 | Planned
34 | 4 · Build — Foundations | Development | UI build — all screens from wireframes | All workstreams | 2026-07-10 | 2026-07-24 | 11 | Planned | Portal · Dashboard · Trade Detail · Compare & Match · Wizard · Admin
35 | 4 · Build — Foundations | ServiceNow PoC | ServiceNow scoped-app scaffold | Protiviti / Snow | 2026-07-07 | 2026-07-11 | 4 | Planned
36 | 4 · Build — Foundations | AWS PoC | AWS environment + deploy base agentic app | AWS / Protiviti | 2026-07-11 | 2026-07-16 | 4 | Planned
37 | 4 · Build — Foundations | Internal Tools | Internal-tool finalisation + setup | IT team | 2026-07-07 | 2026-07-17 | 9 | Planned | Confirm which tool; by when finalised
38 | 5 · Build — Capabilities | Cap 1 — Email Ingestion | Mailbox connection & Graph OAuth (delegated) | All workstreams | 2026-07-14 | 2026-07-16 | 3 | Planned
39 | 5 · Build — Capabilities | Cap 1 — Email Ingestion | Ingestion agent: fetch, store raw email, dedup, attachments | All workstreams | 2026-07-15 | 2026-07-18 | 3 | Planned
40 | 5 · Build — Capabilities | Cap 1 — Email Ingestion | Unit test — Capability 1 | All workstreams | 2026-07-17 | 2026-07-18 | 1 | Planned
41 | 5 · Build — Capabilities | Cap 2 — Email Identification | Classifier (rules + confidence) — is-settlement-allege | All workstreams | 2026-07-14 | 2026-07-17 | 4 | Planned
42 | 5 · Build — Capabilities | Cap 2 — Email Identification | Status from confidence score + aging bucket | All workstreams | 2026-07-17 | 2026-07-18 | 1 | Planned
43 | 5 · Build — Capabilities | Cap 2 — Email Identification | Unit test — Capability 2 | All workstreams | 2026-07-18 | 2026-07-18 | 0 | Planned
44 | 5 · Build — Capabilities | Cap 3 — Outlook Tagging | Tag / categorise emails in Outlook (Graph) | All workstreams | 2026-07-21 | 2026-07-23 | 3 | Planned
45 | 5 · Build — Capabilities | Cap 3 — Outlook Tagging | Unit test — Capability 3 | All workstreams | 2026-07-23 | 2026-07-24 | 2 | Planned
46 | 5 · Build — Capabilities | Cap 4 — Field Extraction | Context parser — extract trade fields (body + attachments) | All workstreams | 2026-07-21 | 2026-07-24 | 4 | Planned
47 | 5 · Build — Capabilities | Cap 4 — Field Extraction | Map extracted fields → data model | All workstreams | 2026-07-22 | 2026-07-24 | 3 | Planned
48 | 5 · Build — Capabilities | Cap 4 — Field Extraction | Unit test — Capability 4 | All workstreams | 2026-07-24 | 2026-07-24 | 1 | Planned
49 | 5 · Build — Capabilities | Cap 5 — Analyst Extraction Confirmation | Trade-detail screen: mail + extracted fields; confirm / edit | Selected workstream | 2026-07-28 | 2026-07-31 | 4 | Planned | Post tool-selection convergence
50 | 5 · Build — Capabilities | Cap 5 — Analyst Extraction Confirmation | Persist confirmation → DB + audit trail / case timeline | Selected workstream | 2026-07-30 | 2026-08-01 | 2 | Planned
51 | 5 · Build — Capabilities | Cap 5 — Analyst Extraction Confirmation | Unit test — Capability 5 | Selected workstream | 2026-08-01 | 2026-08-01 | 0 | Planned
52 | 5 · Build — Capabilities | Cap 6 — Compare & Match | Bank-booked details via Gloss API | Selected workstream | 2026-07-28 | 2026-07-30 | 3 | Planned
53 | 5 · Build — Capabilities | Cap 6 — Compare & Match | Field-level compare & match (100% tick vs mismatch) + score | Selected workstream | 2026-07-29 | 2026-08-01 | 3 | Planned
54 | 5 · Build — Capabilities | Cap 6 — Compare & Match | Unit test — Capability 6 | Selected workstream | 2026-08-01 | 2026-08-01 | 0 | Planned
55 | 5 · Build — Capabilities | Cap 7 — Analyst Action & Write-back | Next actions (chase cpty · escalate MO/SSI · resolve · no-booking · override) | Selected workstream | 2026-08-04 | 2026-08-06 | 3 | Planned
56 | 5 · Build — Capabilities | Cap 7 — Analyst Action & Write-back | Write-back / email generation + case closure | Selected workstream | 2026-08-05 | 2026-08-07 | 3 | Planned
57 | 5 · Build — Capabilities | Cap 7 — Analyst Action & Write-back | Unit test — Capability 7 | Selected workstream | 2026-08-07 | 2026-08-07 | 1 | Planned
58 | 6 · Build — Supporting modules | Onboarding Wizard | Manager wizard builder (Define→Sources→Fields→Mapping→Review/Run) | Selected workstream | 2026-07-21 | 2026-07-31 | 9 | Planned
59 | 6 · Build — Supporting modules | Admin Console | RBAC access matrix, LLM config, user management | Selected workstream | 2026-07-21 | 2026-07-31 | 9 | Planned
60 | 6 · Build — Supporting modules | Audit | Audit trail + case audit timeline | Selected workstream | 2026-07-24 | 2026-07-31 | 6 | Planned
61 | 6 · Build — Supporting modules | Reports | Break summary · weekly trend · counterparty league | Selected workstream | 2026-07-28 | 2026-08-01 | 4 | Planned
62 | 6 · Build — Supporting modules | Integration | Batch process setup | IT team | 2026-07-17 | 2026-07-24 | 6 | Planned
63 | 6 · Build — Supporting modules | Integration | System integration to target systems (write-back) | IT + Sabre | 2026-07-21 | 2026-08-01 | 9 | Planned
64 | 7 · Testing | Testing | Test plan creation | IT team | 2026-07-14 | 2026-07-18 | 4 | In Progress
65 | 7 · Testing | Testing | Test case creation (per capability) | Ops / Protiviti | 2026-07-17 | 2026-07-24 | 6 | Planned
66 | 7 · Testing | Testing | SIT cycle 1 (ingestion → identification → extraction) | All workstreams | 2026-07-27 | 2026-07-31 | 5 | Planned
67 | 7 · Testing | Testing | SIT cycle 2 (confirm → compare & match → action) | Selected workstream | 2026-08-03 | 2026-08-06 | 4 | Planned
68 | 7 · Testing | Testing | Regression + performance smoke | Selected workstream | 2026-08-06 | 2026-08-08 | 2 | Planned
69 | 7 · Testing | Security | Security & data-privacy review | IT / Security | 2026-08-04 | 2026-08-08 | 4 | Planned
70 | 7 · Testing | Milestone | Feature-complete / code freeze | All workstreams | 2026-08-08 | 2026-08-08 | 0 | Planned | Entry to UAT hardening
71 | 8 · UAT & Deployment | Deployment | PoC UAT plan | IT team | 2026-07-17 | 2026-07-21 | 3 | Planned
72 | 8 · UAT & Deployment | Deployment | Deploy to UAT / prod-like (CI/CD) | IT + Protiviti | 2026-08-04 | 2026-08-06 | 3 | Planned
73 | 8 · UAT & Deployment | UAT | UAT cycle 1 (Ops analysts) | Ops | 2026-08-06 | 2026-08-08 | 2 | Planned
74 | 8 · UAT & Deployment | UAT | Defect triage & fixes | All workstreams | 2026-08-07 | 2026-08-11 | 3 | Planned
75 | 8 · UAT & Deployment | UAT | UAT cycle 2 (full E2E) + sign-off | Ops | 2026-08-11 | 2026-08-12 | 2 | Planned | UAT SIGN-OFF milestone
76 | 8 · UAT & Deployment | Approvals | Go-live requirements & approvals (NTI / security) | IT team | 2026-08-11 | 2026-08-13 | 3 | Planned
77 | 8 · UAT & Deployment | Deployment | Pilot user training + runbook / ops handover | Protiviti / Ops | 2026-08-12 | 2026-08-13 | 2 | Planned
78 | 9 · Go-Live / Pilot | Go-Live | Go / No-Go decision | Sabre + IT + Ops | 2026-08-13 | 2026-08-13 | 1 | Planned
79 | 9 · Go-Live / Pilot | Go-Live | Pilot cutover / go-live | All workstreams | 2026-08-14 | 2026-08-14 | 1 | Planned | PILOT READY
80 | 9 · Go-Live / Pilot | Hypercare | Hypercare begins | All workstreams | 2026-08-14 | 2026-08-14 | 1 | Planned | Post go-live support

## Milestones
Key Milestones
Milestone | Target date | Owner | Status
Pre-development complete (BRD · FSD · Jira · wireframes) | 2026-07-04 | Sabre | In Progress
Foundations ready (architecture · data model · envs · repo · access · NTI) | 2026-07-11 | IT team | Planned
Tool / vendor selection decision | 2026-07-18 | Sabre + IT | Planned
Capabilities 1–4 build complete (ingest · identify · tag · extract) | 2026-07-24 | All workstreams | Planned
Capabilities 5–6 complete (confirm · compare & match) | 2026-08-01 | Selected WS | Planned
Capability 7 complete (analyst action & write-back) | 2026-08-07 | Selected WS | Planned
Feature-complete / code freeze | 2026-08-08 | All workstreams | Planned
UAT sign-off | 2026-08-12 | Ops | Planned
Go / No-Go | 2026-08-13 | Sabre + IT + Ops | Planned
PILOT READY — go-live / cutover | 2026-08-14 | All workstreams | Planned

## Weekly Plan
Weekly Plan (reverse-planned to 14-Aug)
Week | Dates | Theme | Key outcomes
W1 | Jul 1 – 3 | Pre-dev close-out | BRD/FSD sign-off · Jira stories · wireframes · synthetic data v1 · SNOW & AWS accesses kicked off
W2 | Jul 6 – 10 | Foundations | Architecture · data model · dev/qa/uat envs · repo · code migration · NTI in progress · golden source · core schema/RBAC
W3 | Jul 13 – 17 | Build Cap 1–2 + UI | Email ingestion · email identification · UI screens · CI/CD scaffold · hosting decision · TOOL-SELECTION gate (18-Jul)
W4 | Jul 20 – 24 | Build Cap 3–4 + supporting | Outlook tagging · field extraction · onboarding wizard · admin console · test cases · batch/integration setup
W5 | Jul 27 – 31 | Build Cap 5–6 (converge) | Analyst confirmation · compare & match · audit trail · reports · SIT cycle 1
W6 | Aug 3 – 7 | Build Cap 7 + integration | Analyst action & write-back · CI/CD to UAT · SIT cycle 2 · security review · regression → feature-complete (8-Aug)
W7 | Aug 10 – 14 | UAT & pilot | UAT cycles 1–2 · defect fixes · UAT sign-off (12) · go/no-go (13) · PILOT CUTOVER → PILOT READY (14-Aug)

## Legend & Assumptions
Status key
Done | Completed & verified.
In Progress | Actively being worked.
Planned | Scheduled; not yet started (YTS).
At Risk | On critical path with a live risk to the date.
TBD | Owner / date to be decided.
Owners / workstreams
IT team | Nomura IT — infra, environments, access, approvals, integration.
Sabre | Delivery / project lead (per source runbook) — planning, decisions, sign-off.
Ops | Nomura Settlement Operations — SMEs, test data, UAT, go/no-go.
Snow team / Santosh | ServiceNow platform team — ServiceNow PoC build & expertise.
AWS team | AWS PoC build & environment.
Protiviti | Delivery partner — solution build across workstreams, wireframes, specs.
NTI team | New-Technology-Introduction — approvals (e.g. Graph API).
BMO / Brett | Supporting approvals / access (AWS tenant, eval instance).
Selected workstream | The single solution chosen at the tool-selection gate (18-Jul) — used for the pilot build.
Seven core capabilities (pilot scope)
1 · Email Ingestion | Connect mailbox (Graph), fetch & store settlement emails, dedup, attachments.
2 · Email Identification | Classify settlement alleges with a confidence score; derive status & aging bucket.
3 · Outlook Tagging | Tag / categorise the identified emails back in Outlook.
4 · Field Extraction | Context parser extracts trade fields from body & attachments; map to the data model.
5 · Analyst Extraction Confirmation | Analyst reviews mail + extracted fields, confirms/edits; persisted with audit.
6 · Compare & Match | Counterparty-submitted vs bank-booked (Gloss API); field-level match & score.
7 · Analyst Action & Write-back | Next actions (chase / escalate / resolve / no-booking / override) + write-back.
Assumptions & risks
Tool selection | Three candidate PoCs (ServiceNow · AWS · Internal) build Cap 1–4 in parallel; one is selected at the 18-Jul gate and carries the pilot build (Cap 5–7 + hardening).
NTI approval | New-tech / Graph-API approval is on the critical path and can take weeks — started early; a delay is the top schedule risk.
Data | Pilot starts on partial synthetic data; full masked production-like data + golden (Gloss) reference to be available by mid-July.
Pilot scope | Pilot = the 7 capabilities end-to-end + Onboarding Wizard, Dashboard, Admin (RBAC), Audit & Reports, on the selected solution, validated via UAT.
Working days | Durations are business days (Mon–Fri); dates are indicative and to be confirmed with each owner.
Status | This plan is PROPOSED for review; owners/ETAs to be confirmed and baselined at the next steering meeting.