## Summary
YES BANK ¦ AI Powered Audit Intelligence System
Programme Effort Estimate & Commercial Summary - Protiviti India (R&C) | [11 empty] | Ratesheet
Basis: RFI ver 1.2 dated 14/08/2026 ¦ Rates: India - R&C card @ 1 USD = INR 80.5 ¦ Fixed Fee (Inclusive of Outlays)
DOMESTIC PRICING BASIS - effort halved uniformly across every activity line (all 9 workstreams, all 207 tasks, all grades) against the initial estimate. Recovery % and contribution margin are unchanged.
# | Workstream | Tasks | Hours | Person- Days | Standard Fee (INR) | Proposed Fee (INR) | Recovery % | Staff Cost (INR) | Mgmt Fee 5% (INR) | Direct Cost (INR) | Contribution (INR) | Net CM %
1 | Continuous Control Monitoring (CCM) | 23 | 2499 | 312.375 | 16708220 | 6000000 | 35.91% | 4297200 | 300000 | 4597200 | 1402800 | 23.38%
2 | Pre-Audit Checks Automation | 22 | 2185 | 273.125 | 14252160 | 5000000 | 35.08% | 3627768 | 250000 | 3877768 | 1122232 | 22.44%
3 | VKYC Audit Automation | 20 | 1625 | 203.125 | 10865330 | 4250000 | 39.12% | 2780592 | 212500 | 2993092 | 1256908 | 29.57%
4 | KYC Audit Automation | 25 | 2333 | 291.625 | 14999420 | 5500000 | 36.67% | 3796320 | 275000 | 4071320 | 1428680 | 25.98%
5 | Audit Checklist Automation | 20 | 1287 | 160.875 | 8438810 | 3250000 | 38.51% | 2152848 | 162500 | 2315348 | 934652 | 28.76%
6 | Data Analytics for Internal Audit (AI/ML) | 26 | 2542 | 317.75 | 16830130 | 6750000 | 40.11% | 4322544 | 337500 | 4660044 | 2089956 | 30.96%
7 | Audit Life Cycle Management (ALCM) | 23 | 2133 | 266.625 | 13756660 | 4750000 | 34.53% | 3493176 | 237500 | 3730676 | 1019324 | 21.46%
8 | Agentic AI for Audit Functions | 28 | 3168 | 396 | 21105590 | 8750000 | 41.46% | 5428344 | 437500 | 5865844 | 2884156 | 32.96%
9 | ChatBot for Policies, SOPs & Document Retrieval | 20 | 1319 | 164.875 | 8575590 | 3250000 | 37.9% | 2198736 | 162500 | 2361236 | 888764 | 27.35%
| PROGRAMME TOTAL | 207 | 19091 | 2386.375 | 125531910 | 47500000 | 37.84% | 32097528 | 2375000 | 34472528 | 13027472 | 27.43%
TOTAL EFFORT (HOURS) |  |  | PERSON-DAYS (8H) |  |  | STANDARD FEE (INR) |  |  | PROPOSED FEE (INR)
19091 |  |  | 2386.375 |  |  | 125531910 |  |  | 47500000
BUDGETED RECOVERY % |  |  | NET CONTRIBUTION MARGIN % |  |  | NET REVENUE / HOUR (INR) |  |  | BLENDED COST / HOUR (INR)
37.84% |  |  | 27.43% |  |  | 2488.0834 |  |  | 1681.2911
PROGRAMME GRADE MIX
Grade | Designation | Hours | Mix % | Cost (INR)
MD | Managing Director | 43 | 0.2252% | 928800
SD | Senior Director | 0 | 0% | 0
DIR | Director | 452 | 2.368% | 4339200
AD | Associate Director | 1330 | 6.967% | 7341600
SR. MGR | Senior Manager | 890 | 4.662% | 3310800
MGR | Manager | 0 | 0% | 0
DM | Deputy Manager | 2836 | 14.86% | 4594320
SR. CONS. | Senior Consultant | 3636 | 19.05% | 4035960
CON3 | Consultant 3 | 4952 | 25.94% | 4278528
CON2 | Consultant 2 | 4952 | 25.94% | 3268320
CON1 | Consultant 1 | 0 | 0% | 0
ANLST. | Analyst | 0 | 0% | 0
TOTAL |  | 19091 | 100% | 32097528
BASIS OF ESTIMATE & KEY ASSUMPTIONS
0. DOMESTIC BASIS: hours on every activity line have been halved against the initial estimate, per review direction. Because Standard Fee, Staff Cost and Proposed Fee all scale with hours, Recovery % and Net CM % are unchanged. Delivery risk of the reduced effort is called out in note 13.
1. Effort is built bottom-up: each workstream is decomposed into delivery tasks and loaded by resource grade. Standard Fee = hours x India-R&C chargeout rates; Staff Cost = hours x cost rates (Ratesheet tab).
2. Proposed Fee is a commercial input (blue cells, column G / cell D on each tool sheet). Recovery % and Contribution Margin recalculate automatically. Change the fee, not the derived cells.
3. Direct Cost = standard staff cost + 5% management fee, consistent with the Protiviti project template. Outlays / OPE are budgeted at NIL - see assumption 7.
4. Delivery assumed from India (Home Office, R&C service line). No sub-contractor or other-office cost included.
5. Excludes: hardware, OS and Oracle DB licences (supplied by YES BANK per RFI 5.3); GPU infrastructure for in-perimeter LLM hosting; third-party software, middleware and tool licences; ATS / AMC beyond go-live.
6. Excludes post go-live onsite L1 & L2 support resources (RFI 3.2 item 9) - to be priced separately as a recurring annual managed-service line.
7. Outlays are NIL in this build. Travel to YES BANK House (Santacruz, Mumbai), LLM / API consumption, vector-store and OCR licences must be added to the Expenses sheet before submission, or they erode the contribution margin directly.
8. Assumes the 5,000+ concurrent-user NFR is clarified downward to Internal Audit population. If literal, add load-tier infrastructure and performance-engineering effort.
9. Assumes ALCM replaces Pentana (migration utility included). If ALCM must instead integrate with a retained Pentana, workstream 7 reduces and workstream 1 integration effort increases.
10. 'Integration' tasks are scoped at the source-system counts named in the RFI. Each additional source system beyond that list is a change request.
11. Excludes prototype / FSD / wireframe effort required at RFI response stage - that is pre-sales investment, not delivery effort.
12. Indicative schedule at this effort level: 12-15 months at an average of 6-7 FTE, assuming workstreams 1, 2 and 7 run first and 6 & 8 follow the data foundation.
13. DELIVERY RISK OF THE HALVED BASIS: the scope in the RFI is unchanged, so this estimate now assumes significant reuse of existing Protiviti accelerators (the CCM rules engine, dashboard and workflow assets already built), an agile fixed-capacity model rather than fixed-scope, and YES BANK-side ownership of data extracts, environment provisioning and UAT execution. If those three assumptions do not hold, effort reverts toward the original basis.

## Ratesheet
R A T E S H E E T - India / R&C
Chargeout & cost rates per the Protiviti India project template (effective 1-Jul-23). All source rates in USD; INR derived at the FX rate below.
FX Rate (INR per USD) |  | 80.5 |  |  |  |  | < Summary
Grade | Designation | Chargeout USD/hr | Cost USD/hr | Chargeout INR/hr | Cost INR/hr
MD | Managing Director | 373.0435 | 268.323 | 30030 | 21600
SD | Senior Director | 310.559 | 124.2236 | 25000 | 10000
DIR | Director | 274.2857 | 119.2547 | 22080 | 9600
AD | Associate Director | 217.8882 | 68.5714 | 17540 | 5520
SR. MGR | Senior Manager | 185.2174 | 46.2112 | 14910 | 3720
MGR | Manager | 125.2174 | 31.3043 | 10080 | 2520
DM | Deputy Manager | 93.5404 | 20.1242 | 7530 | 1620
SR. CONS. | Senior Consultant | 62.6087 | 13.7888 | 5040 | 1110
CON3 | Consultant 3 | 49.441 | 10.7329 | 3980 | 864
CON2 | Consultant 2 | 45.8385 | 8.1988 | 3690 | 660
CON1 | Consultant 1 | 39.7516 | 6.2609 | 3200 | 504
ANLST. | Analyst | 20.2484 | 3.7267 | 1630 | 300
LOOKUP ROW (used by every tool sheet - do not reorder)
Grade | MD | SD | DIR | AD | SR. MGR | MGR | DM | SR. CONS. | CON3 | CON2 | CON1 | ANLST.
Chargeout INR/hr | 30030 | 25000 | 22080 | 17540 | 14910 | 10080 | 7530 | 5040 | 3980 | 3690 | 3200 | 1630
Cost INR/hr | 21600 | 10000 | 9600 | 5520 | 3720 | 2520 | 1620 | 1110 | 864 | 660 | 504 | 300

## 1. CCM
Protiviti Member Firm (India) | [19 empty] | Project Template 2023 Apr.23
Project Template - Fixed Fee Inclusive Outlays
Organisation: | India - R&C | [19 empty] | < Summary | RATE ENGINE (auto)
Client Legal Name: | YES BANK Ltd. |  |  | Resource Plan (Home Office) - Budgeted Hours by Task and Resource Category | [17 empty] | Standard Revenue (INR) | 16708220
Project Description: | Continuous Control Monitoring (CCM) |  |  | Task Name |  | Business Unit |  | MD | SD | DIR | AD | SR. MGR | MGR | DM | SR. CONS. | CON3 | CON2 | CON1 | ANLST. | TOTAL | Ratesheet | Standard Staff Cost (INR) | 4297200
Billing Currency: | INR |  |  |  |  | Country | Service line | [14 empty] | Blended chargeout / hr | 6685.9624
Project Type: | Fixed Fee (Incl. Outlays) |  |  | Requirement Gathering, Control Universe & Feasibility Study |  | India | R&C | 2 |  | 12 | 12 |  |  | 20 | 20 | 24 | 24 |  |  | 114 |  | Blended cost / hr | 1719.5678
|  |  |  | Technical Architecture, Design & Planning |  | India | R&C | 2 |  | 16 | 16 |  |  | 20 | 20 | 20 | 20 |  |  | 114
|  |  |  | Data Model & Database Design |  | India | R&C | 1 |  | 6 | 8 |  |  | 16 | 16 | 24 | 24 |  |  | 95
|  |  |  | Data Warehouse & Source System Ingestion Framework |  | India | R&C |  |  | 4 | 12 |  |  | 24 | 32 | 48 | 48 |  |  | 168
|  |  |  | Control Rule Engine & Rule Library Build |  | India | R&C |  |  | 6 | 16 |  |  | 28 | 36 | 56 | 56 |  |  | 198
|  |  |  | No-Code Rule & Threshold Configurator |  | India | R&C |  |  | 2 | 8 |  |  | 20 | 24 | 36 | 36 |  |  | 126
|  |  |  | Exception Management, Risk Scoring & Alerting Engine |  | India | R&C |  |  | 2 | 10 |  |  | 24 | 32 | 44 | 44 |  |  | 156
|  |  |  | Remediation Workflow & Auditee Assignment |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 98
|  |  |  | Correlation, Root-Cause & Trend Analytics |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 28 | 28 |  |  | 102
|  |  |  | Change & Configuration Drift Detection |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | Orchestration & Automated Response Hooks |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | API Layer & Microservices Implementation |  | India | R&C |  |  | 4 | 8 |  |  | 20 | 24 | 40 | 40 |  |  | 136
|  |  |  | Frontend Design & Real-Time Control Dashboards |  | India | R&C |  |  |  | 8 |  |  | 24 | 32 | 48 | 48 |  |  | 160
|  |  |  | FE & BE Integration |  | India | R&C |  |  |  | 6 |  |  | 16 | 24 | 28 | 28 |  |  | 102
|  |  |  | Regulatory Evidence & ACB Report Generation |  | India | R&C |  |  | 2 | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 74
|  |  |  | Audit Management Application (Pentana) Integration |  | India | R&C |  |  | 2 | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 74
|  |  |  | Auth, RBAC, NFR & Security Implementation |  | India | R&C |  |  |  | 8 |  |  | 16 | 20 | 24 | 24 |  |  | 92
|  |  |  | Component Testing & SIT |  | India | R&C |  |  | 2 | 8 |  |  | 20 | 28 | 36 | 36 |  |  | 130
|  |  |  | User Acceptance Testing (incl. Bug Fixing) |  | India | R&C |  |  | 1 | 6 |  |  | 12 | 20 | 28 | 28 |  |  | 95
|  |  |  | Documentation (Technical, User, DR/BCP) |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | PMO & Programme Governance |  | India | R&C |  |  |  |  | 140 | [7 empty] | 140
|  |  |  | Go-live & Hypercare Support |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 56
|  |  |  | Handover & Knowledge Transfer |  | India | R&C | 1 |  | 4 | 4 |  |  | 8 | 12 | 12 | 12 |  |  | 53
|  |  |  | Total |  |  |  | 6 | 0 | 65 | 168 | 140 | 0 | 368 | 472 | 640 | 640 | 0 | 0 | 2499
[6 empty] | Project Mix |  | 0.2401% | 0% | 2.601% | 6.723% | 5.602% | 0% | 14.73% | 18.89% | 25.61% | 25.61% | 0% | 0%
F E E B R E A K D O W N | [5 empty] | All Values in ( INR ) |  |  |  | What if analysis - FYI Only
Total Engagement Value |  | 6000000 | Expenses Budgeting | [6 empty] | Pricing Tool - Home Office |  |  |  |  | Fee Amount |  | Recovery %
Description |  | Org./ Name |  | Hours Breakdown | Fee Breakdown | Budgeted Outlays |  |  |  | Standard Fee |  |  |  |  | 16708220 |  | 16708220
Home Office |  | India - R&C |  | 2499 | 6000000 | 0 |  |  |  | Proposed Fee (Home Office) - India - R&C |  |  |  |  | 6000000 |  | 6000000
Sub-Contractor (3rd party) |  |  |  | 0 | 0 | 0 |  |  |  | Planned Fee Adjustment (PFA) |  |  |  |  | 10708220 |  | 10708220
|  |  |  | 0 | 0 | 0 |  |  |  | PFA % |  |  |  |  | 64.09% |  | 64.09%
|  |  |  | 0 | 0 | 0 |  |  |  | Recovery % |  |  |  |  | 35.91% |  | 35.91%
GST |  |  |  | 0 | 0 | 0
Total |  |  |  | 2499 | 6000000 | 0
| Budgeted Recovery % |  |  | 35.91%
[10 empty] | Gross Fee |  | Net Fee |  | Net CM |  | Gross CM
[10 empty] | Fee | Per/Hr | Fee | Per/Hr | % |  | % |  | Margin |  | Staff Cost
[9 empty] | INR | 6000000 | 2400.9604 | 6000000 | 2400.9604 | 23.38% |  | 23.38% |  | 1702800 |  | 4297200
|  | Data to be entered / editable | [7 empty] | Gross Contribution Margin is derived after considering direct staff cost, management fees, Sub-contractor cost and other direct cost. Net Contribution Margin is derived after considering direct staff cost, management fees and other direct cost.
Calculated - do not overwrite

## 2. Pre-Audit Checks
Protiviti Member Firm (India) | [19 empty] | Project Template 2023 Apr.23
Project Template - Fixed Fee Inclusive Outlays
Organisation: | India - R&C | [19 empty] | < Summary | RATE ENGINE (auto)
Client Legal Name: | YES BANK Ltd. |  |  | Resource Plan (Home Office) - Budgeted Hours by Task and Resource Category | [17 empty] | Standard Revenue (INR) | 14252160
Project Description: | Pre-Audit Checks Automation |  |  | Task Name |  | Business Unit |  | MD | SD | DIR | AD | SR. MGR | MGR | DM | SR. CONS. | CON3 | CON2 | CON1 | ANLST. | TOTAL | Ratesheet | Standard Staff Cost (INR) | 3627768
Billing Currency: | INR |  |  |  |  | Country | Service line | [14 empty] | Blended chargeout / hr | 6522.7277
Project Type: | Fixed Fee (Incl. Outlays) |  |  | Requirement Gathering & Audit Programme Study |  | India | R&C | 2 |  | 10 | 10 |  |  | 16 | 16 | 20 | 20 |  |  | 94 |  | Blended cost / hr | 1660.3057
|  |  |  | Technical Architecture, Design & Planning |  | India | R&C | 2 |  | 12 | 12 |  |  | 16 | 16 | 16 | 16 |  |  | 90
|  |  |  | Data Model & Database Design |  | India | R&C | 1 |  | 4 | 6 |  |  | 12 | 16 | 20 | 20 |  |  | 79
|  |  |  | Multi-System Ingestion (CBS, LOS, LMS, GL, HRMS, CRM) |  | India | R&C |  |  | 4 | 12 |  |  | 28 | 36 | 56 | 56 |  |  | 192
|  |  |  | File-Based Ingestion & Automated Schema Validation |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 24 | 24 |  |  | 80
|  |  |  | Pre-Audit Validation Rule Library (5 control domains) |  | India | R&C |  |  | 4 | 12 |  |  | 24 | 32 | 48 | 48 |  |  | 168
|  |  |  | Custom Rule Builder & What-If Simulation |  | India | R&C |  |  | 2 | 8 |  |  | 20 | 24 | 36 | 36 |  |  | 126
|  |  |  | Automated Sampling Engine (risk/random/stratified) |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 32 | 32 |  |  | 110
|  |  |  | Dynamic Checklist Generation & Auto-Population |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 98
|  |  |  | Exception Reporting, Severity Tagging & Risk Flags |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 98
|  |  |  | API Layer & Microservices Implementation |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 20 | 32 | 32 |  |  | 108
|  |  |  | Frontend Design & Audit Readiness Dashboards |  | India | R&C |  |  |  | 8 |  |  | 20 | 28 | 40 | 40 |  |  | 136
|  |  |  | FE & BE Integration |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 24 | 24 |  |  | 90
|  |  |  | Workflow, Query Management & Collaboration |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 98
|  |  |  | Reporting & Export Engine (PDF / Excel / Word) |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | Auth, RBAC, Audit Trail & NFR Implementation |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 24 | 24 |  |  | 90
|  |  |  | Component Testing & SIT |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 24 | 32 | 32 |  |  | 112
|  |  |  | User Acceptance Testing (incl. Bug Fixing) |  | India | R&C |  |  | 1 | 4 |  |  | 12 | 16 | 24 | 24 |  |  | 81
|  |  |  | Documentation (Technical, User, DR/BCP) |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 56
|  |  |  | PMO & Programme Governance |  | India | R&C |  |  |  |  | 110 | [7 empty] | 110
|  |  |  | Go-live & Hypercare Support |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 12 | 12 |  |  | 48
|  |  |  | Handover & Knowledge Transfer |  | India | R&C | 1 |  | 4 | 4 |  |  | 8 | 8 | 12 | 12 |  |  | 49
|  |  |  | Total |  |  |  | 6 | 0 | 47 | 142 | 110 | 0 | 324 | 412 | 572 | 572 | 0 | 0 | 2185
[6 empty] | Project Mix |  | 0.2746% | 0% | 2.151% | 6.499% | 5.034% | 0% | 14.83% | 18.86% | 26.18% | 26.18% | 0% | 0%
F E E B R E A K D O W N | [5 empty] | All Values in ( INR ) |  |  |  | What if analysis - FYI Only
Total Engagement Value |  | 5000000 | Expenses Budgeting | [6 empty] | Pricing Tool - Home Office |  |  |  |  | Fee Amount |  | Recovery %
Description |  | Org./ Name |  | Hours Breakdown | Fee Breakdown | Budgeted Outlays |  |  |  | Standard Fee |  |  |  |  | 14252160 |  | 14252160
Home Office |  | India - R&C |  | 2185 | 5000000 | 0 |  |  |  | Proposed Fee (Home Office) - India - R&C |  |  |  |  | 5000000 |  | 5000000
Sub-Contractor (3rd party) |  |  |  | 0 | 0 | 0 |  |  |  | Planned Fee Adjustment (PFA) |  |  |  |  | 9252160 |  | 9252160
|  |  |  | 0 | 0 | 0 |  |  |  | PFA % |  |  |  |  | 64.92% |  | 64.92%
|  |  |  | 0 | 0 | 0 |  |  |  | Recovery % |  |  |  |  | 35.08% |  | 35.08%
GST |  |  |  | 0 | 0 | 0
Total |  |  |  | 2185 | 5000000 | 0
| Budgeted Recovery % |  |  | 35.08%
[10 empty] | Gross Fee |  | Net Fee |  | Net CM |  | Gross CM
[10 empty] | Fee | Per/Hr | Fee | Per/Hr | % |  | % |  | Margin |  | Staff Cost
[9 empty] | INR | 5000000 | 2288.3295 | 5000000 | 2288.3295 | 22.44% |  | 22.44% |  | 1372232 |  | 3627768
|  | Data to be entered / editable | [7 empty] | Gross Contribution Margin is derived after considering direct staff cost, management fees, Sub-contractor cost and other direct cost. Net Contribution Margin is derived after considering direct staff cost, management fees and other direct cost.
Calculated - do not overwrite

## 3. VKYC Audit
Protiviti Member Firm (India) | [19 empty] | Project Template 2023 Apr.23
Project Template - Fixed Fee Inclusive Outlays
Organisation: | India - R&C | [19 empty] | < Summary | RATE ENGINE (auto)
Client Legal Name: | YES BANK Ltd. |  |  | Resource Plan (Home Office) - Budgeted Hours by Task and Resource Category | [17 empty] | Standard Revenue (INR) | 10865330
Project Description: | VKYC Audit Automation |  |  | Task Name |  | Business Unit |  | MD | SD | DIR | AD | SR. MGR | MGR | DM | SR. CONS. | CON3 | CON2 | CON1 | ANLST. | TOTAL | Ratesheet | Standard Staff Cost (INR) | 2780592
Billing Currency: | INR |  |  |  |  | Country | Service line | [14 empty] | Blended chargeout / hr | 6686.3569
Project Type: | Fixed Fee (Incl. Outlays) |  |  | Requirement Gathering & VKYC Process Study |  | India | R&C | 1 |  | 8 | 8 |  |  | 12 | 12 | 16 | 16 |  |  | 73 |  | Blended cost / hr | 1711.1335
|  |  |  | Technical Architecture, Design & Planning |  | India | R&C | 1 |  | 8 | 8 |  |  | 12 | 12 | 12 | 12 |  |  | 65
|  |  |  | Data Model & Media Store Design |  | India | R&C |  |  | 4 | 6 |  |  | 12 | 12 | 16 | 16 |  |  | 66
|  |  |  | VKYC Artefact Ingestion (video, audio, form data) |  | India | R&C |  |  | 2 | 8 |  |  | 20 | 24 | 36 | 36 |  |  | 126
|  |  |  | Speech-to-Text & Audio Analytics Pipeline |  | India | R&C |  |  | 4 | 12 |  |  | 24 | 28 | 36 | 36 |  |  | 140
|  |  |  | Cognitive Text & NLP Analytics on Transcripts |  | India | R&C |  |  | 4 | 12 |  |  | 20 | 24 | 32 | 32 |  |  | 124
|  |  |  | Face Match / Liveness Evidence Validation |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 28 | 28 |  |  | 102
|  |  |  | Rule-Driven VKYC Compliance Evaluation Engine |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 28 | 28 |  |  | 102
|  |  |  | Exception Detection, Evidencing & Audit Trail |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | API Layer & VKYC Repository Integration |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 24 | 24 |  |  | 80
|  |  |  | Frontend Design & Reviewer Console |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 98
|  |  |  | FE & BE Integration |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | Model Validation, Accuracy Tuning & Bias Testing |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 20 | 20 |  |  | 86
|  |  |  | Auth, RBAC, Audit Trail & NFR Implementation |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | Component Testing & SIT |  | India | R&C |  |  | 1 | 4 |  |  | 12 | 16 | 24 | 24 |  |  | 81
|  |  |  | User Acceptance Testing (incl. Bug Fixing) |  | India | R&C |  |  | 1 | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 57
|  |  |  | Documentation (Technical, User, Model Card) |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 12 | 12 |  |  | 48
|  |  |  | PMO & Programme Governance |  | India | R&C |  |  |  |  | 80 | [7 empty] | 80
|  |  |  | Go-live & Hypercare Support |  | India | R&C |  |  |  | 2 |  |  | 8 | 8 | 12 | 12 |  |  | 42
|  |  |  | Handover & Knowledge Transfer |  | India | R&C | 1 |  | 2 | 4 |  |  | 8 | 8 | 8 | 8 |  |  | 39
|  |  |  | Total |  |  |  | 3 | 0 | 40 | 118 | 80 | 0 | 256 | 312 | 408 | 408 | 0 | 0 | 1625
[6 empty] | Project Mix |  | 0.1846% | 0% | 2.462% | 7.262% | 4.923% | 0% | 15.75% | 19.2% | 25.11% | 25.11% | 0% | 0%
F E E B R E A K D O W N | [5 empty] | All Values in ( INR ) |  |  |  | What if analysis - FYI Only
Total Engagement Value |  | 4250000 | Expenses Budgeting | [6 empty] | Pricing Tool - Home Office |  |  |  |  | Fee Amount |  | Recovery %
Description |  | Org./ Name |  | Hours Breakdown | Fee Breakdown | Budgeted Outlays |  |  |  | Standard Fee |  |  |  |  | 10865330 |  | 10865330
Home Office |  | India - R&C |  | 1625 | 4250000 | 0 |  |  |  | Proposed Fee (Home Office) - India - R&C |  |  |  |  | 4250000 |  | 4250000
Sub-Contractor (3rd party) |  |  |  | 0 | 0 | 0 |  |  |  | Planned Fee Adjustment (PFA) |  |  |  |  | 6615330 |  | 6615330
|  |  |  | 0 | 0 | 0 |  |  |  | PFA % |  |  |  |  | 60.88% |  | 60.88%
|  |  |  | 0 | 0 | 0 |  |  |  | Recovery % |  |  |  |  | 39.12% |  | 39.12%
GST |  |  |  | 0 | 0 | 0
Total |  |  |  | 1625 | 4250000 | 0
| Budgeted Recovery % |  |  | 39.12%
[10 empty] | Gross Fee |  | Net Fee |  | Net CM |  | Gross CM
[10 empty] | Fee | Per/Hr | Fee | Per/Hr | % |  | % |  | Margin |  | Staff Cost
[9 empty] | INR | 4250000 | 2615.3846 | 4250000 | 2615.3846 | 29.57% |  | 29.57% |  | 1469408 |  | 2780592
|  | Data to be entered / editable | [7 empty] | Gross Contribution Margin is derived after considering direct staff cost, management fees, Sub-contractor cost and other direct cost. Net Contribution Margin is derived after considering direct staff cost, management fees and other direct cost.
Calculated - do not overwrite

## 4. KYC Audit
Protiviti Member Firm (India) | [19 empty] | Project Template 2023 Apr.23
Project Template - Fixed Fee Inclusive Outlays
Organisation: | India - R&C | [19 empty] | < Summary | RATE ENGINE (auto)
Client Legal Name: | YES BANK Ltd. |  |  | Resource Plan (Home Office) - Budgeted Hours by Task and Resource Category | [17 empty] | Standard Revenue (INR) | 14999420
Project Description: | KYC Audit Automation |  |  | Task Name |  | Business Unit |  | MD | SD | DIR | AD | SR. MGR | MGR | DM | SR. CONS. | CON3 | CON2 | CON1 | ANLST. | TOTAL | Ratesheet | Standard Staff Cost (INR) | 3796320
Billing Currency: | INR |  |  |  |  | Country | Service line | [14 empty] | Blended chargeout / hr | 6429.2413
Project Type: | Fixed Fee (Incl. Outlays) |  |  | Requirement Gathering & RBI KYC Master Direction Study |  | India | R&C | 2 |  | 10 | 10 |  |  | 16 | 16 | 20 | 20 |  |  | 94 |  | Blended cost / hr | 1627.2267
|  |  |  | Technical Architecture, Design & Planning |  | India | R&C | 2 |  | 10 | 10 |  |  | 12 | 12 | 16 | 16 |  |  | 78
|  |  |  | Data Model & Database Design |  | India | R&C | 1 |  | 4 | 6 |  |  | 12 | 16 | 20 | 20 |  |  | 79
|  |  |  | KYC Data Ingestion (CBS, CRM, CIF, AML, LOS, DMS) |  | India | R&C |  |  | 4 | 12 |  |  | 24 | 32 | 48 | 48 |  |  | 168
|  |  |  | OCR / Intelligent Document Processing Pipeline |  | India | R&C |  |  | 4 | 12 |  |  | 24 | 28 | 44 | 44 |  |  | 156
|  |  |  | Identity Verification Rules (PAN/Aadhaar/Passport/VID/DL) |  | India | R&C |  |  | 2 | 8 |  |  | 20 | 24 | 36 | 36 |  |  | 126
|  |  |  | Address, Demographic & Document Expiry Validation |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 98
|  |  |  | CDD / EDD & Customer Risk Categorisation Validation |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 28 | 28 |  |  | 102
|  |  |  | Periodic KYC Review & FATCA / CRS Compliance Checks |  | India | R&C |  |  |  | 6 |  |  | 12 | 16 | 24 | 24 |  |  | 82
|  |  |  | Exception Detection, Severity Ranking & Bulk Closure |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 98
|  |  |  | Automated & Stratified Sampling Engine |  | India | R&C |  |  |  | 6 |  |  | 12 | 16 | 24 | 24 |  |  | 82
|  |  |  | Dynamic KYC Checklist Automation |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | No-Code Rule Engine, Versioning & Impact Simulation |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 32 | 32 |  |  | 110
|  |  |  | API Layer & Microservices Implementation |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 32 | 32 |  |  | 106
|  |  |  | Frontend Design & Exception / Heat-Map Dashboards |  | India | R&C |  |  |  | 8 |  |  | 20 | 24 | 36 | 36 |  |  | 124
|  |  |  | FE & BE Integration |  | India | R&C |  |  |  | 6 |  |  | 12 | 20 | 24 | 24 |  |  | 86
|  |  |  | Workflow, Query Management & Collaboration |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 24 | 24 |  |  | 80
|  |  |  | Reporting Suite (6 standard regulatory reports) |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | Auth, RBAC, Audit Trail & NFR Implementation |  | India | R&C |  |  |  | 6 |  |  | 12 | 16 | 20 | 20 |  |  | 74
|  |  |  | Component Testing & SIT |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 24 | 32 | 32 |  |  | 112
|  |  |  | User Acceptance Testing (incl. Bug Fixing) |  | India | R&C |  |  | 1 | 4 |  |  | 12 | 16 | 24 | 24 |  |  | 81
|  |  |  | Documentation (Technical, User, DR/BCP) |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 56
|  |  |  | PMO & Programme Governance |  | India | R&C |  |  |  |  | 100 | [7 empty] | 100
|  |  |  | Go-live & Hypercare Support |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 12 | 12 |  |  | 48
|  |  |  | Handover & Knowledge Transfer |  | India | R&C | 1 |  | 4 | 4 |  |  | 8 | 8 | 12 | 12 |  |  | 49
|  |  |  | Total |  |  |  | 6 | 0 | 45 | 158 | 100 | 0 | 344 | 440 | 620 | 620 | 0 | 0 | 2333
[6 empty] | Project Mix |  | 0.2572% | 0% | 1.929% | 6.772% | 4.286% | 0% | 14.74% | 18.86% | 26.58% | 26.58% | 0% | 0%
F E E B R E A K D O W N | [5 empty] | All Values in ( INR ) |  |  |  | What if analysis - FYI Only
Total Engagement Value |  | 5500000 | Expenses Budgeting | [6 empty] | Pricing Tool - Home Office |  |  |  |  | Fee Amount |  | Recovery %
Description |  | Org./ Name |  | Hours Breakdown | Fee Breakdown | Budgeted Outlays |  |  |  | Standard Fee |  |  |  |  | 14999420 |  | 14999420
Home Office |  | India - R&C |  | 2333 | 5500000 | 0 |  |  |  | Proposed Fee (Home Office) - India - R&C |  |  |  |  | 5500000 |  | 5500000
Sub-Contractor (3rd party) |  |  |  | 0 | 0 | 0 |  |  |  | Planned Fee Adjustment (PFA) |  |  |  |  | 9499420 |  | 9499420
|  |  |  | 0 | 0 | 0 |  |  |  | PFA % |  |  |  |  | 63.33% |  | 63.33%
|  |  |  | 0 | 0 | 0 |  |  |  | Recovery % |  |  |  |  | 36.67% |  | 36.67%
GST |  |  |  | 0 | 0 | 0
Total |  |  |  | 2333 | 5500000 | 0
| Budgeted Recovery % |  |  | 36.67%
[10 empty] | Gross Fee |  | Net Fee |  | Net CM |  | Gross CM
[10 empty] | Fee | Per/Hr | Fee | Per/Hr | % |  | % |  | Margin |  | Staff Cost
[9 empty] | INR | 5500000 | 2357.4796 | 5500000 | 2357.4796 | 25.98% |  | 25.98% |  | 1703680 |  | 3796320
|  | Data to be entered / editable | [7 empty] | Gross Contribution Margin is derived after considering direct staff cost, management fees, Sub-contractor cost and other direct cost. Net Contribution Margin is derived after considering direct staff cost, management fees and other direct cost.
Calculated - do not overwrite

## 5. Checklist Automation
Protiviti Member Firm (India) | [19 empty] | Project Template 2023 Apr.23
Project Template - Fixed Fee Inclusive Outlays
Organisation: | India - R&C | [19 empty] | < Summary | RATE ENGINE (auto)
Client Legal Name: | YES BANK Ltd. |  |  | Resource Plan (Home Office) - Budgeted Hours by Task and Resource Category | [17 empty] | Standard Revenue (INR) | 8438810
Project Description: | Audit Checklist Automation |  |  | Task Name |  | Business Unit |  | MD | SD | DIR | AD | SR. MGR | MGR | DM | SR. CONS. | CON3 | CON2 | CON1 | ANLST. | TOTAL | Ratesheet | Standard Staff Cost (INR) | 2152848
Billing Currency: | INR |  |  |  |  | Country | Service line | [14 empty] | Blended chargeout / hr | 6556.9619
Project Type: | Fixed Fee (Incl. Outlays) |  |  | Requirement Gathering & Regulatory Corpus Study |  | India | R&C | 1 |  | 6 | 8 |  |  | 12 | 12 | 12 | 12 |  |  | 63 |  | Blended cost / hr | 1672.7646
|  |  |  | Technical Architecture, Design & Planning |  | India | R&C | 1 |  | 6 | 6 |  |  | 8 | 12 | 12 | 12 |  |  | 57
|  |  |  | Data Model & Central Rule Repository Design |  | India | R&C |  |  | 2 | 6 |  |  | 12 | 12 | 16 | 16 |  |  | 64
|  |  |  | Regulatory / Circular / SOP Ingestion Pipeline |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 100
|  |  |  | NLP Extraction & Requirement Interpretation |  | India | R&C |  |  | 4 | 8 |  |  | 16 | 20 | 28 | 28 |  |  | 104
|  |  |  | Regulation-to-Control Mapping Repository |  | India | R&C |  |  | 2 | 6 |  |  | 12 | 16 | 24 | 24 |  |  | 84
|  |  |  | Checklist Generation Engine (process / entity / risk-wise) |  | India | R&C |  |  | 2 | 6 |  |  | 12 | 16 | 24 | 24 |  |  | 84
|  |  |  | Auto-Update on Regulatory Change & Traceability |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | Version Control, Approval Workflow & Audit Trail |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 56
|  |  |  | Auditor Customisation & Evidence Tagging |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 56
|  |  |  | API Layer & Integration with ALCM / Pre-Audit |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 20 | 20 |  |  | 64
|  |  |  | Frontend Design & Checklist Console |  | India | R&C |  |  |  | 6 |  |  | 12 | 20 | 24 | 24 |  |  | 86
|  |  |  | FE & BE Integration |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 56
|  |  |  | Auth, RBAC, Audit Trail & NFR Implementation |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 12 | 12 |  |  | 48
|  |  |  | Component Testing & SIT |  | India | R&C |  |  | 1 | 4 |  |  | 8 | 16 | 20 | 20 |  |  | 69
|  |  |  | User Acceptance Testing (incl. Bug Fixing) |  | India | R&C |  |  | 1 | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 57
|  |  |  | Documentation (Technical, User) |  | India | R&C |  |  |  | 2 |  |  | 8 | 8 | 12 | 12 |  |  | 42
|  |  |  | PMO & Programme Governance |  | India | R&C |  |  |  |  | 60 | [7 empty] | 60
|  |  |  | Go-live & Hypercare Support |  | India | R&C |  |  |  | 2 |  |  | 4 | 8 | 8 | 8 |  |  | 30
|  |  |  | Handover & Knowledge Transfer |  | India | R&C | 1 |  | 2 | 4 |  |  | 4 | 8 | 8 | 8 |  |  | 35
|  |  |  | Total |  |  |  | 3 | 0 | 28 | 92 | 60 | 0 | 184 | 256 | 332 | 332 | 0 | 0 | 1287
[6 empty] | Project Mix |  | 0.2331% | 0% | 2.176% | 7.148% | 4.662% | 0% | 14.3% | 19.89% | 25.8% | 25.8% | 0% | 0%
F E E B R E A K D O W N | [5 empty] | All Values in ( INR ) |  |  |  | What if analysis - FYI Only
Total Engagement Value |  | 3250000 | Expenses Budgeting | [6 empty] | Pricing Tool - Home Office |  |  |  |  | Fee Amount |  | Recovery %
Description |  | Org./ Name |  | Hours Breakdown | Fee Breakdown | Budgeted Outlays |  |  |  | Standard Fee |  |  |  |  | 8438810 |  | 8438810
Home Office |  | India - R&C |  | 1287 | 3250000 | 0 |  |  |  | Proposed Fee (Home Office) - India - R&C |  |  |  |  | 3250000 |  | 3250000
Sub-Contractor (3rd party) |  |  |  | 0 | 0 | 0 |  |  |  | Planned Fee Adjustment (PFA) |  |  |  |  | 5188810 |  | 5188810
|  |  |  | 0 | 0 | 0 |  |  |  | PFA % |  |  |  |  | 61.49% |  | 61.49%
|  |  |  | 0 | 0 | 0 |  |  |  | Recovery % |  |  |  |  | 38.51% |  | 38.51%
GST |  |  |  | 0 | 0 | 0
Total |  |  |  | 1287 | 3250000 | 0
| Budgeted Recovery % |  |  | 38.51%
[10 empty] | Gross Fee |  | Net Fee |  | Net CM |  | Gross CM
[10 empty] | Fee | Per/Hr | Fee | Per/Hr | % |  | % |  | Margin |  | Staff Cost
[9 empty] | INR | 3250000 | 2525.2525 | 3250000 | 2525.2525 | 28.76% |  | 28.76% |  | 1097152 |  | 2152848
|  | Data to be entered / editable | [7 empty] | Gross Contribution Margin is derived after considering direct staff cost, management fees, Sub-contractor cost and other direct cost. Net Contribution Margin is derived after considering direct staff cost, management fees and other direct cost.
Calculated - do not overwrite

## 6. Data Analytics
Protiviti Member Firm (India) | [19 empty] | Project Template 2023 Apr.23
Project Template - Fixed Fee Inclusive Outlays
Organisation: | India - R&C | [19 empty] | < Summary | RATE ENGINE (auto)
Client Legal Name: | YES BANK Ltd. |  |  | Resource Plan (Home Office) - Budgeted Hours by Task and Resource Category | [17 empty] | Standard Revenue (INR) | 16830130
Project Description: | Data Analytics for Internal Audit (AI/ML) |  |  | Task Name |  | Business Unit |  | MD | SD | DIR | AD | SR. MGR | MGR | DM | SR. CONS. | CON3 | CON2 | CON1 | ANLST. | TOTAL | Ratesheet | Standard Staff Cost (INR) | 4322544
Billing Currency: | INR |  |  |  |  | Country | Service line | [14 empty] | Blended chargeout / hr | 6620.8222
Project Type: | Fixed Fee (Incl. Outlays) |  |  | Requirement Gathering & Analytics Use-Case Definition |  | India | R&C | 2 |  | 10 | 10 |  |  | 16 | 16 | 20 | 20 |  |  | 94 |  | Blended cost / hr | 1700.45
|  |  |  | Technical Architecture, Design & Planning (MLOps) |  | India | R&C | 2 |  | 12 | 12 |  |  | 16 | 16 | 16 | 16 |  |  | 90
|  |  |  | Data Model, Feature Store & Lakehouse Design |  | India | R&C |  |  | 6 | 10 |  |  | 16 | 20 | 28 | 28 |  |  | 108
|  |  |  | Multi-Source Data Ingestion & Pipelines |  | India | R&C |  |  | 4 | 8 |  |  | 20 | 28 | 44 | 44 |  |  | 148
|  |  |  | AI-Enabled Data Profiling & Quality Scoring |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 32 | 32 |  |  | 110
|  |  |  | Automated Data Cleaning & Transformation Pipelines |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 32 | 32 |  |  | 106
|  |  |  | Anomaly & Outlier Detection Models |  | India | R&C |  |  | 4 | 12 |  |  | 24 | 28 | 40 | 40 |  |  | 148
|  |  |  | Predictive Risk Modelling & Forecasting |  | India | R&C |  |  | 4 | 12 |  |  | 20 | 24 | 36 | 36 |  |  | 132
|  |  |  | Intelligent Segmentation & Clustering |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 28 | 28 |  |  | 102
|  |  |  | ML-Based Exception Scoring & Feedback Learning |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 28 | 28 |  |  | 102
|  |  |  | Intelligent / Risk-Based Sampling Models |  | India | R&C |  |  | 2 | 6 |  |  | 12 | 16 | 24 | 24 |  |  | 84
|  |  |  | NLP Models for Documents, Policies & Circulars |  | India | R&C |  |  | 4 | 10 |  |  | 20 | 24 | 32 | 32 |  |  | 122
|  |  |  | Explainable AI (SHAP / LIME) Layer |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 24 | 24 |  |  | 94
|  |  |  | Model Registry, Versioning & Governance |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 24 | 24 |  |  | 94
|  |  |  | Model Drift, Bias & Performance Monitoring |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 20 | 24 | 24 |  |  | 92
|  |  |  | Controlled Re-training & Approval Workflow |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | API Layer & Microservices Implementation |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 32 | 32 |  |  | 106
|  |  |  | Frontend Design & AI Insight Dashboards |  | India | R&C |  |  |  | 8 |  |  | 20 | 24 | 36 | 36 |  |  | 124
|  |  |  | FE & BE Integration |  | India | R&C |  |  |  | 6 |  |  | 12 | 20 | 24 | 24 |  |  | 86
|  |  |  | Auth, RBAC, Data Lineage & NFR Implementation |  | India | R&C |  |  |  | 6 |  |  | 12 | 16 | 20 | 20 |  |  | 74
|  |  |  | Component Testing, Model Validation & SIT |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 24 | 32 | 32 |  |  | 114
|  |  |  | User Acceptance Testing (incl. Bug Fixing) |  | India | R&C |  |  | 1 | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 73
|  |  |  | Documentation (Architecture, Model Cards, Runbooks) |  | India | R&C |  |  |  | 4 |  |  | 12 | 12 | 16 | 16 |  |  | 60
|  |  |  | PMO & Programme Governance |  | India | R&C |  |  |  |  | 110 | [7 empty] | 110
|  |  |  | Go-live & Hypercare Support |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 12 | 12 |  |  | 48
|  |  |  | Handover & Knowledge Transfer |  | India | R&C | 1 |  | 4 | 4 |  |  | 8 | 8 | 12 | 12 |  |  | 49
|  |  |  | Total |  |  |  | 5 | 0 | 65 | 186 | 110 | 0 | 384 | 480 | 656 | 656 | 0 | 0 | 2542
[6 empty] | Project Mix |  | 0.1967% | 0% | 2.557% | 7.317% | 4.327% | 0% | 15.11% | 18.88% | 25.81% | 25.81% | 0% | 0%
F E E B R E A K D O W N | [5 empty] | All Values in ( INR ) |  |  |  | What if analysis - FYI Only
Total Engagement Value |  | 6750000 | Expenses Budgeting | [6 empty] | Pricing Tool - Home Office |  |  |  |  | Fee Amount |  | Recovery %
Description |  | Org./ Name |  | Hours Breakdown | Fee Breakdown | Budgeted Outlays |  |  |  | Standard Fee |  |  |  |  | 16830130 |  | 16830130
Home Office |  | India - R&C |  | 2542 | 6750000 | 0 |  |  |  | Proposed Fee (Home Office) - India - R&C |  |  |  |  | 6750000 |  | 6750000
Sub-Contractor (3rd party) |  |  |  | 0 | 0 | 0 |  |  |  | Planned Fee Adjustment (PFA) |  |  |  |  | 10080130 |  | 10080130
|  |  |  | 0 | 0 | 0 |  |  |  | PFA % |  |  |  |  | 59.89% |  | 59.89%
|  |  |  | 0 | 0 | 0 |  |  |  | Recovery % |  |  |  |  | 40.11% |  | 40.11%
GST |  |  |  | 0 | 0 | 0
Total |  |  |  | 2542 | 6750000 | 0
| Budgeted Recovery % |  |  | 40.11%
[10 empty] | Gross Fee |  | Net Fee |  | Net CM |  | Gross CM
[10 empty] | Fee | Per/Hr | Fee | Per/Hr | % |  | % |  | Margin |  | Staff Cost
[9 empty] | INR | 6750000 | 2655.3895 | 6750000 | 2655.3895 | 30.96% |  | 30.96% |  | 2427456 |  | 4322544
|  | Data to be entered / editable | [7 empty] | Gross Contribution Margin is derived after considering direct staff cost, management fees, Sub-contractor cost and other direct cost. Net Contribution Margin is derived after considering direct staff cost, management fees and other direct cost.
Calculated - do not overwrite

## 7. ALCM
Protiviti Member Firm (India) | [19 empty] | Project Template 2023 Apr.23
Project Template - Fixed Fee Inclusive Outlays
Organisation: | India - R&C | [19 empty] | < Summary | RATE ENGINE (auto)
Client Legal Name: | YES BANK Ltd. |  |  | Resource Plan (Home Office) - Budgeted Hours by Task and Resource Category | [17 empty] | Standard Revenue (INR) | 13756660
Project Description: | Audit Life Cycle Management (ALCM) |  |  | Task Name |  | Business Unit |  | MD | SD | DIR | AD | SR. MGR | MGR | DM | SR. CONS. | CON3 | CON2 | CON1 | ANLST. | TOTAL | Ratesheet | Standard Staff Cost (INR) | 3493176
Billing Currency: | INR |  |  |  |  | Country | Service line | [14 empty] | Blended chargeout / hr | 6449.4421
Project Type: | Fixed Fee (Incl. Outlays) |  |  | Requirement Gathering & Audit Lifecycle Process Study |  | India | R&C | 2 |  | 10 | 10 |  |  | 16 | 16 | 20 | 20 |  |  | 94 |  | Blended cost / hr | 1637.6821
|  |  |  | Technical Architecture, Design & Planning |  | India | R&C | 2 |  | 10 | 10 |  |  | 12 | 12 | 16 | 16 |  |  | 78
|  |  |  | Data Model & Database Design |  | India | R&C | 1 |  | 4 | 6 |  |  | 12 | 16 | 20 | 20 |  |  | 79
|  |  |  | Audit Planning, Universe & Scheduling Module |  | India | R&C |  |  | 2 | 8 |  |  | 20 | 24 | 36 | 36 |  |  | 126
|  |  |  | Audit Scope & Programme Definition Module |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 100
|  |  |  | Fieldwork & Workpaper Documentation Module |  | India | R&C |  |  | 2 | 8 |  |  | 20 | 28 | 40 | 40 |  |  | 138
|  |  |  | Findings & Issue Management Module |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 32 | 32 |  |  | 106
|  |  |  | Reporting, QA Review & Report Release Workflow |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 20 | 32 | 32 |  |  | 108
|  |  |  | Action Tracking, Follow-Up & Audit Closure |  | India | R&C |  |  |  | 6 |  |  | 12 | 16 | 24 | 24 |  |  | 82
|  |  |  | Resource Allocation & Schedule Management |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | Configurable Workflow & Approval Engine |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 100
|  |  |  | API Layer & Integration with CCM / Analytics / Checklist |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 20 | 32 | 32 |  |  | 108
|  |  |  | Pentana Migration & Historical Data Migration Utility |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 100
|  |  |  | Frontend Design & Audit Status Dashboards |  | India | R&C |  |  |  | 8 |  |  | 20 | 28 | 40 | 40 |  |  | 136
|  |  |  | FE & BE Integration |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 24 | 24 |  |  | 90
|  |  |  | Mobile-Responsive UI & Offline Sync Capability |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 24 | 24 |  |  | 80
|  |  |  | Auth, RBAC, SoD, Audit Trail & NFR Implementation |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 24 | 24 |  |  | 90
|  |  |  | Component Testing & SIT |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 24 | 32 | 32 |  |  | 112
|  |  |  | User Acceptance Testing (incl. Bug Fixing) |  | India | R&C |  |  | 1 | 4 |  |  | 12 | 16 | 24 | 24 |  |  | 81
|  |  |  | Documentation (Technical, User, DR/BCP) |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 56
|  |  |  | PMO & Programme Governance |  | India | R&C |  |  |  |  | 100 | [7 empty] | 100
|  |  |  | Go-live & Hypercare Support |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 12 | 12 |  |  | 48
|  |  |  | Handover & Knowledge Transfer |  | India | R&C | 1 |  | 4 | 4 |  |  | 8 | 8 | 12 | 12 |  |  | 49
|  |  |  | Total |  |  |  | 6 | 0 | 45 | 134 | 100 | 0 | 316 | 404 | 564 | 564 | 0 | 0 | 2133
[6 empty] | Project Mix |  | 0.2813% | 0% | 2.11% | 6.282% | 4.688% | 0% | 14.81% | 18.94% | 26.44% | 26.44% | 0% | 0%
F E E B R E A K D O W N | [5 empty] | All Values in ( INR ) |  |  |  | What if analysis - FYI Only
Total Engagement Value |  | 4750000 | Expenses Budgeting | [6 empty] | Pricing Tool - Home Office |  |  |  |  | Fee Amount |  | Recovery %
Description |  | Org./ Name |  | Hours Breakdown | Fee Breakdown | Budgeted Outlays |  |  |  | Standard Fee |  |  |  |  | 13756660 |  | 13756660
Home Office |  | India - R&C |  | 2133 | 4750000 | 0 |  |  |  | Proposed Fee (Home Office) - India - R&C |  |  |  |  | 4750000 |  | 4750000
Sub-Contractor (3rd party) |  |  |  | 0 | 0 | 0 |  |  |  | Planned Fee Adjustment (PFA) |  |  |  |  | 9006660 |  | 9006660
|  |  |  | 0 | 0 | 0 |  |  |  | PFA % |  |  |  |  | 65.47% |  | 65.47%
|  |  |  | 0 | 0 | 0 |  |  |  | Recovery % |  |  |  |  | 34.53% |  | 34.53%
GST |  |  |  | 0 | 0 | 0
Total |  |  |  | 2133 | 4750000 | 0
| Budgeted Recovery % |  |  | 34.53%
[10 empty] | Gross Fee |  | Net Fee |  | Net CM |  | Gross CM
[10 empty] | Fee | Per/Hr | Fee | Per/Hr | % |  | % |  | Margin |  | Staff Cost
[9 empty] | INR | 4750000 | 2226.9105 | 4750000 | 2226.9105 | 21.46% |  | 21.46% |  | 1256824 |  | 3493176
|  | Data to be entered / editable | [7 empty] | Gross Contribution Margin is derived after considering direct staff cost, management fees, Sub-contractor cost and other direct cost. Net Contribution Margin is derived after considering direct staff cost, management fees and other direct cost.
Calculated - do not overwrite

## 8. Agentic AI
Protiviti Member Firm (India) | [19 empty] | Project Template 2023 Apr.23
Project Template - Fixed Fee Inclusive Outlays
Organisation: | India - R&C | [19 empty] | < Summary | RATE ENGINE (auto)
Client Legal Name: | YES BANK Ltd. |  |  | Resource Plan (Home Office) - Budgeted Hours by Task and Resource Category | [17 empty] | Standard Revenue (INR) | 21105590
Project Description: | Agentic AI for Audit Functions |  |  | Task Name |  | Business Unit |  | MD | SD | DIR | AD | SR. MGR | MGR | DM | SR. CONS. | CON3 | CON2 | CON1 | ANLST. | TOTAL | Ratesheet | Standard Staff Cost (INR) | 5428344
Billing Currency: | INR |  |  |  |  | Country | Service line | [14 empty] | Blended chargeout / hr | 6662.1181
Project Type: | Fixed Fee (Incl. Outlays) |  |  | Requirement Gathering & Agentic Use-Case Definition |  | India | R&C | 2 |  | 12 | 12 |  |  | 16 | 16 | 20 | 20 |  |  | 98 |  | Blended cost / hr | 1713.4924
|  |  |  | Agentic Architecture, Design & Planning |  | India | R&C | 2 |  | 16 | 16 |  |  | 20 | 20 | 20 | 20 |  |  | 114
|  |  |  | In-Perimeter LLM Hosting, GPU Sizing & Model Selection |  | India | R&C |  |  | 6 | 12 |  |  | 24 | 28 | 36 | 36 |  |  | 142
|  |  |  | Agent Orchestration Framework & Task Planner |  | India | R&C |  |  | 6 | 16 |  |  | 28 | 36 | 52 | 52 |  |  | 190
|  |  |  | Tool / Function Layer (data, test, evidence connectors) |  | India | R&C |  |  | 4 | 12 |  |  | 24 | 32 | 48 | 48 |  |  | 168
|  |  |  | Contextual Reasoning & Audit Knowledge Grounding |  | India | R&C |  |  | 4 | 12 |  |  | 20 | 28 | 40 | 40 |  |  | 144
|  |  |  | AI-Driven Audit Planning & Scoping Agent |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 32 | 32 |  |  | 110
|  |  |  | AI-Generated Checklist & Test Procedure Agent |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 28 | 28 |  |  | 102
|  |  |  | Agentic Data Analytics & Automated Testing Agent |  | India | R&C |  |  | 4 | 12 |  |  | 24 | 28 | 40 | 40 |  |  | 148
|  |  |  | Autonomous Exception Identification & Severity Agent |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 32 | 32 |  |  | 110
|  |  |  | Intelligent Sampling Agent |  | India | R&C |  |  |  | 6 |  |  | 12 | 16 | 24 | 24 |  |  | 82
|  |  |  | Audit Workpaper Generation Agent |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 32 | 32 |  |  | 110
|  |  |  | Autonomous Query Management Agent |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 98
|  |  |  | GenAI Report & Narrative Generation (4 summary levels) |  | India | R&C |  |  | 4 | 10 |  |  | 20 | 24 | 36 | 36 |  |  | 130
|  |  |  | Explainability, Reasoning Chains & Immutable Logging |  | India | R&C |  |  | 4 | 10 |  |  | 20 | 24 | 32 | 32 |  |  | 122
|  |  |  | Human-in-the-Loop Control Plane & Override Workflow |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 28 | 28 |  |  | 102
|  |  |  | Guardrails: Prompt Injection, Data Leakage, Adversarial |  | India | R&C |  |  | 4 | 12 |  |  | 20 | 24 | 32 | 32 |  |  | 124
|  |  |  | Agent / Model Registry, Versioning, Rollback & Drift |  | India | R&C |  |  | 2 | 8 |  |  | 16 | 20 | 24 | 24 |  |  | 94
|  |  |  | API Layer & Microservices Implementation |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 32 | 32 |  |  | 106
|  |  |  | Frontend Design & Agent Console / Trace Viewer |  | India | R&C |  |  |  | 8 |  |  | 20 | 28 | 40 | 40 |  |  | 136
|  |  |  | FE & BE Integration |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 24 | 24 |  |  | 90
|  |  |  | Auth, RBAC, NFR & Enterprise Security Implementation |  | India | R&C |  |  |  | 6 |  |  | 16 | 20 | 24 | 24 |  |  | 90
|  |  |  | Component Testing, Red-Teaming & SIT |  | India | R&C |  |  | 4 | 10 |  |  | 20 | 28 | 36 | 36 |  |  | 134
|  |  |  | User Acceptance Testing (incl. Bug Fixing) |  | India | R&C |  |  | 1 | 6 |  |  | 12 | 20 | 28 | 28 |  |  | 95
|  |  |  | Documentation (Architecture, Agent Cards, AI Governance) |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 20 | 20 |  |  | 72
|  |  |  | PMO & Programme Governance |  | India | R&C |  |  |  |  | 140 | [7 empty] | 140
|  |  |  | Go-live & Hypercare Support |  | India | R&C |  |  |  | 4 |  |  | 12 | 16 | 16 | 16 |  |  | 64
|  |  |  | Handover & Knowledge Transfer |  | India | R&C | 1 |  | 4 | 4 |  |  | 8 | 12 | 12 | 12 |  |  | 53
|  |  |  | Total |  |  |  | 5 | 0 | 85 | 238 | 140 | 0 | 472 | 596 | 816 | 816 | 0 | 0 | 3168
[6 empty] | Project Mix |  | 0.1578% | 0% | 2.683% | 7.513% | 4.419% | 0% | 14.9% | 18.81% | 25.76% | 25.76% | 0% | 0%
F E E B R E A K D O W N | [5 empty] | All Values in ( INR ) |  |  |  | What if analysis - FYI Only
Total Engagement Value |  | 8750000 | Expenses Budgeting | [6 empty] | Pricing Tool - Home Office |  |  |  |  | Fee Amount |  | Recovery %
Description |  | Org./ Name |  | Hours Breakdown | Fee Breakdown | Budgeted Outlays |  |  |  | Standard Fee |  |  |  |  | 21105590 |  | 21105590
Home Office |  | India - R&C |  | 3168 | 8750000 | 0 |  |  |  | Proposed Fee (Home Office) - India - R&C |  |  |  |  | 8750000 |  | 8750000
Sub-Contractor (3rd party) |  |  |  | 0 | 0 | 0 |  |  |  | Planned Fee Adjustment (PFA) |  |  |  |  | 12355590 |  | 12355590
|  |  |  | 0 | 0 | 0 |  |  |  | PFA % |  |  |  |  | 58.54% |  | 58.54%
|  |  |  | 0 | 0 | 0 |  |  |  | Recovery % |  |  |  |  | 41.46% |  | 41.46%
GST |  |  |  | 0 | 0 | 0
Total |  |  |  | 3168 | 8750000 | 0
| Budgeted Recovery % |  |  | 41.46%
[10 empty] | Gross Fee |  | Net Fee |  | Net CM |  | Gross CM
[10 empty] | Fee | Per/Hr | Fee | Per/Hr | % |  | % |  | Margin |  | Staff Cost
[9 empty] | INR | 8750000 | 2761.9949 | 8750000 | 2761.9949 | 32.96% |  | 32.96% |  | 3321656 |  | 5428344
|  | Data to be entered / editable | [7 empty] | Gross Contribution Margin is derived after considering direct staff cost, management fees, Sub-contractor cost and other direct cost. Net Contribution Margin is derived after considering direct staff cost, management fees and other direct cost.
Calculated - do not overwrite

## 9. ChatBot
Protiviti Member Firm (India) | [19 empty] | Project Template 2023 Apr.23
Project Template - Fixed Fee Inclusive Outlays
Organisation: | India - R&C | [19 empty] | < Summary | RATE ENGINE (auto)
Client Legal Name: | YES BANK Ltd. |  |  | Resource Plan (Home Office) - Budgeted Hours by Task and Resource Category | [17 empty] | Standard Revenue (INR) | 8575590
Project Description: | ChatBot for Policies, SOPs & Document Retrieval |  |  | Task Name |  | Business Unit |  | MD | SD | DIR | AD | SR. MGR | MGR | DM | SR. CONS. | CON3 | CON2 | CON1 | ANLST. | TOTAL | Ratesheet | Standard Staff Cost (INR) | 2198736
Billing Currency: | INR |  |  |  |  | Country | Service line | [14 empty] | Blended chargeout / hr | 6501.5845
Project Type: | Fixed Fee (Incl. Outlays) |  |  | Requirement Gathering & Document Corpus Study |  | India | R&C | 1 |  | 6 | 6 |  |  | 12 | 12 | 16 | 16 |  |  | 69 |  | Blended cost / hr | 1666.9719
|  |  |  | Technical Architecture, Design & Planning (RAG) |  | India | R&C | 1 |  | 6 | 8 |  |  | 12 | 12 | 12 | 12 |  |  | 63
|  |  |  | Document Corpus Ingestion, Parsing & Chunking |  | India | R&C |  |  | 2 | 6 |  |  | 16 | 20 | 28 | 28 |  |  | 100
|  |  |  | Embedding Pipeline & Vector Store Setup |  | India | R&C |  |  | 2 | 6 |  |  | 12 | 16 | 24 | 24 |  |  | 84
|  |  |  | Retrieval, Re-ranking & Answer Synthesis |  | India | R&C |  |  | 4 | 8 |  |  | 16 | 20 | 28 | 28 |  |  | 104
|  |  |  | Citation, Grounding & Hallucination Controls |  | India | R&C |  |  | 2 | 6 |  |  | 12 | 16 | 20 | 20 |  |  | 76
|  |  |  | Role-Based Document ACL & Secure Information Delivery |  | India | R&C |  |  | 2 | 6 |  |  | 12 | 16 | 20 | 20 |  |  | 76
|  |  |  | Conversational UI & Chat Console |  | India | R&C |  |  |  | 6 |  |  | 12 | 20 | 24 | 24 |  |  | 86
|  |  |  | FE & BE Integration |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 56
|  |  |  | Summarisation & Audit Artefact Retrieval Features |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 20 | 20 |  |  | 64
|  |  |  | API Layer & Integration with ALCM / Checklist |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 56
|  |  |  | Guardrails, Prompt Injection Defence & PII Redaction |  | India | R&C |  |  | 2 | 6 |  |  | 12 | 16 | 20 | 20 |  |  | 76
|  |  |  | Auth, RBAC, Audit Trail & NFR Implementation |  | India | R&C |  |  |  | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 56
|  |  |  | Accuracy Evaluation & Response Quality Tuning |  | India | R&C |  |  | 2 | 6 |  |  | 12 | 16 | 20 | 20 |  |  | 76
|  |  |  | Component Testing & SIT |  | India | R&C |  |  | 1 | 4 |  |  | 8 | 16 | 20 | 20 |  |  | 69
|  |  |  | User Acceptance Testing (incl. Bug Fixing) |  | India | R&C |  |  | 1 | 4 |  |  | 8 | 12 | 16 | 16 |  |  | 57
|  |  |  | Documentation (Technical, User) |  | India | R&C |  |  |  | 2 |  |  | 4 | 8 | 12 | 12 |  |  | 38
|  |  |  | PMO & Programme Governance |  | India | R&C |  |  |  |  | 50 | [7 empty] | 50
|  |  |  | Go-live & Hypercare Support |  | India | R&C |  |  |  | 2 |  |  | 4 | 8 | 8 | 8 |  |  | 30
|  |  |  | Handover & Knowledge Transfer |  | India | R&C | 1 |  | 2 | 2 |  |  | 4 | 8 | 8 | 8 |  |  | 33
|  |  |  | Total |  |  |  | 3 | 0 | 32 | 94 | 50 | 0 | 188 | 264 | 344 | 344 | 0 | 0 | 1319
[6 empty] | Project Mix |  | 0.2274% | 0% | 2.426% | 7.127% | 3.791% | 0% | 14.25% | 20.02% | 26.08% | 26.08% | 0% | 0%
F E E B R E A K D O W N | [5 empty] | All Values in ( INR ) |  |  |  | What if analysis - FYI Only
Total Engagement Value |  | 3250000 | Expenses Budgeting | [6 empty] | Pricing Tool - Home Office |  |  |  |  | Fee Amount |  | Recovery %
Description |  | Org./ Name |  | Hours Breakdown | Fee Breakdown | Budgeted Outlays |  |  |  | Standard Fee |  |  |  |  | 8575590 |  | 8575590
Home Office |  | India - R&C |  | 1319 | 3250000 | 0 |  |  |  | Proposed Fee (Home Office) - India - R&C |  |  |  |  | 3250000 |  | 3250000
Sub-Contractor (3rd party) |  |  |  | 0 | 0 | 0 |  |  |  | Planned Fee Adjustment (PFA) |  |  |  |  | 5325590 |  | 5325590
|  |  |  | 0 | 0 | 0 |  |  |  | PFA % |  |  |  |  | 62.1% |  | 62.1%
|  |  |  | 0 | 0 | 0 |  |  |  | Recovery % |  |  |  |  | 37.9% |  | 37.9%
GST |  |  |  | 0 | 0 | 0
Total |  |  |  | 1319 | 3250000 | 0
| Budgeted Recovery % |  |  | 37.9%
[10 empty] | Gross Fee |  | Net Fee |  | Net CM |  | Gross CM
[10 empty] | Fee | Per/Hr | Fee | Per/Hr | % |  | % |  | Margin |  | Staff Cost
[9 empty] | INR | 3250000 | 2463.9879 | 3250000 | 2463.9879 | 27.35% |  | 27.35% |  | 1051264 |  | 2198736
|  | Data to be entered / editable | [7 empty] | Gross Contribution Margin is derived after considering direct staff cost, management fees, Sub-contractor cost and other direct cost. Net Contribution Margin is derived after considering direct staff cost, management fees and other direct cost.
Calculated - do not overwrite